MERIDIAN BANK BERHAD

Credit Quality Recovery & Digital Transformation Strategy | FY2025–2026

1. EXECUTIVE OVERVIEW

Meridian Bank Berhad is a mid-tier Malaysian commercial bank with total assets of MYR 68.4 billion, total loans of MYR 49.1 billion, and 248 branches nationwide. FY2024 net profit declined 22.7% YoY to MYR 554 million — primarily driven by a surge in Personal Financing NPL to 14.2% and the consequent increase in loan loss provisions (+84% YoY). This strategy document outlines the bank's dual-track recovery agenda: (1) arresting the credit quality deterioration in the retail portfolio, and (2) accelerating digital banking to improve cost efficiency and improve customer acquisition economics.

2. CREDIT QUALITY CRISIS — PERSONAL FINANCING

Personal Financing NPL reached 14.2% in Q1 FY2025 — approximately 4x the BNM industry threshold of 3.5%. This has triggered a BNM supervisory enquiry under BNM's PCOS (Prudential Credit Oversight Standards) framework.

2.1 Root Cause Analysis

Aggressive growth phase FY2021-FY2022: Meridian Bank grew Personal Financing book by 42% over 24 months, targeting B40 and M40 income segments via digital channels

Credit scoring model not calibrated for post-pandemic income volatility: median borrower income in this segment fell 12-18% post-MCO cessation relief (Dec 2022)

Collection infrastructure under-invested: Meridian's collection team (128 FTE) is handling 4x the volume it was designed for

Third-party agent collections: 3 external agencies engaged — 2 have generated BNM complaints for aggressive collection practices (formal warning issued Jan 2025)

Rate sensitivity: Most Personal Financing is at variable OPR+3.5%. OPR increases in FY2022-FY2023 pushed effective rates above borrower serviceability

2.2 Recovery Plan

Debt Restructuring Programme (DRP): Proactive outreach to 48,000 distressed borrowers. Offer: extend tenor by 24-36 months + 2% rate reduction for 12 months (conditional on timely payment). Target: 60% participation rate. Estimated NPL reduction: 6-8 percentage points over 18 months

Collection Transformation: Replace 2 non-compliant agencies with a single in-house collection unit. Hire 80 additional trained collectors. Deploy AI-powered early warning system (FICO Debt Manager) — already in procurement

Credit Scoring Recalibration: Engage TransUnion CTOS + internal data lake to rebuild retail credit scorecard. Model to include open banking data, utility bill payment history, CCRIS data. Expected improvement in Gini coefficient: from 0.42 to 0.58

Provision Build: FY2025 provisioning budget: MYR 680M (conservative). ECL model reviewed by Deloitte — findings incorporated. Provision coverage target: 80% by Dec 2025 (current 42.4%)

────────────────────────────────────────────────────────────────────────────────

3. DIGITAL BANKING TRANSFORMATION

3.1 MeridianGo App — Enhancement Roadmap

MeridianGo mobile app has 412,000 MAU — growing 45% YoY but still significantly below peers (Maybank2u: 12M MAU). App Store rating: 4.2 (target 4.5). Three priority feature releases in FY2025:

Q2 2025 — Digital Loan Origination: End-to-end digital personal loan application with eKYC. Eliminate 14-day manual processing. Target: 72-hour approval. Reduce branch-dependent applications from 68% to 30%

Q3 2025 — SmartSave AI: AI-powered savings and spending insights. Round-up savings feature. Gamification layer (savings challenges). Target: MYR 1.2B in new deposits from app users

Q4 2025 — Open Banking Marketplace: 5 fintech partnerships: insurance aggregation (Great Eastern, Allianz), investment (Fundsupermart), remittance (Merchantrade, Wise). Revenue sharing model. Target: MYR 48M non-interest income

3.2 Branch Rationalisation

Meridian's 248 branches cost MYR 284M/yr to operate (22.4% of total overhead). Target: rationalise to 180 branches by FY2027. Strategy:

Convert 42 underperforming branches to 'micro-branches' (3 staff, advisory-only — no cash tellers)

Close 26 branches in <2km proximity to other Meridian branches (overlap map completed)

Partner with 7-Eleven and MyNews for CDM (Cash Deposit Machine) placement in vacated areas

Reinvest MYR 84M of savings into digital and contact centre capabilities

────────────────────────────────────────────────────────────────────────────────

4. CAPITAL PLAN FY2025-FY2026

CET1 ratio has declined from 13.8% (Q1 FY2024) to 11.8% (Q1 FY2025) — driven by provision build and loan growth. Below internal target of 13.5%. BNM minimum: 7.0%.

Rights Issue (proposed): MYR 1.2B rights issue at 10% discount to NTA — target Q3 2025. Expected CET1 uplift: +1.4 percentage points. Pending Board approval and SC prospectus clearance

Asset Recycling: Dispose of non-core investment properties (3 assets, estimated MYR 480M). Net proceeds after deferred tax: MYR 380M — CET1 uplift: +0.5pp

RWA Optimisation: Reduce concentration in high-RWA SME real estate financing — target MYR 2.4B RWA reduction. CET1 uplift: +0.3pp

Target CET1 by Dec 2026: 13.0% — within 0.5pp of internal target. Full restoration to 13.5% by FY2027