## Open findings
FY2026 Internal Audit — open findings tracker
ID | Theme | Severity | Owner | Target close | Status | Latest update
F-2026-001 | Vendor master — duplicates | High | Group Procurement | 2026-07-31 | In progress | Cleansing run scheduled 2026-06-12
F-2026-002 | Privileged access — shared accounts | Critical | Group IT Security | 2026-06-15 | In progress | Shared admin retired on 18 of 22 platforms
F-2026-003 | JML — leaver access not revoked | High | Group HR | 2026-08-30 | In progress | Automation pilot on Workday in test
F-2026-004 | Vendor risk tiering — outdated | Medium | Group Procurement | 2026-09-30 | Open | Awaiting refreshed risk model
F-2026-005 | Contract repository — version control | Medium | Group Legal | 2026-10-31 | Open | Migration plan being scoped
F-2026-006 | Segregation of duties — AP team | High | Group Finance | 2026-08-15 | In progress | Workflow split deployed in 3 of 5 markets
F-2026-007 | Vendor due diligence — sanctions screening | High | Group Compliance | 2026-07-15 | In progress | Vendor refresh batch 2 of 4 in train
F-2026-008 | Data classification — missing labels | Medium | Group IT Security | 2026-11-30 | Open | Awaiting tooling rollout
F-2026-009 | Penetration test — high finding | High | Group IT Security | 2026-07-31 | In progress | Patch deployment in change window
F-2026-010 | Records retention — over-retention | Medium | Group Legal | 2026-12-15 | Open | Policy refresh underway
F-2026-011 | Travel expense — late approvals | Low | Group Finance | 2026-09-30 | Open | Workflow change scoped
F-2026-012 | Outsourcing — annual attestation gap | Medium | Group Risk | 2026-08-31 | In progress | 10 of 14 attestations received
F-2026-013 | Business continuity — exercise overdue | High | Group Risk | 2026-07-31 | In progress | Tabletop scheduled 2026-06-20
F-2026-014 | Whistleblowing — case ageing | High | Group Compliance | 2026-06-30 | In progress | Backlog cleared from 14 to 4 cases
F-2026-015 | Conflict of interest — annual declarations | Medium | Group HR | 2026-09-30 | Open | Refresh launch in July

## Closed FY26 YTD
Findings closed in FY2026 year-to-date
ID | Theme | Severity | Closed on | Effectiveness validation
F-2025-082 | Period-end accruals | Medium | 2026-02-15 | Sample tested — pass
F-2025-091 | Inventory cycle-count coverage | Medium | 2026-03-04 | Sample tested — pass
F-2025-103 | IT change advisory board attendance | Low | 2026-03-22 | Self-attestation accepted
F-2025-118 | Bank reconciliation ageing | Medium | 2026-04-11 | Sample tested — pass
F-2025-124 | Vendor PO three-way match | High | 2026-04-25 | Sample tested — pass
F-2025-131 | Customer credit limit overrides | Medium | 2026-05-08 | Sample tested — pass
F-2025-137 | Cyber-incident response runbook | High | 2026-05-19 | Tabletop validated
F-2025-142 | Data-room access reviews | Medium | 2026-05-29 | Sample tested — pass

## Ageing summary
Open findings — ageing buckets
Severity | 0-30 days | 31-90 days | 91-180 days | 180+ days
Critical | 1 | 0 | 0 | 0
High | 3 | 2 | 1 | 0
Medium | 2 | 3 | 1 | 1
Low | 0 | 1 | 0 | 0