## Register
BNK 04 NPL Recovery Tracker
Source file: BNK_04_NPL_Recovery_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Decision | Medium | Daichi Maruyama | 2026-01-08 | 2026-06-12 | In progress | Re-baselined this week
ITM-002 | Capex business case approval pending | Issue | High | Hadar Caspit | 2026-04-12 | 2026-09-18 | Blocked | Pending external review
ITM-003 | Renewal of MSA — top 5 client | Issue | Medium | Daichi Maruyama | 2026-03-07 | 2026-08-26 | In progress | Pending external review
ITM-004 | S/4HANA cut-over readiness gap | Action | Medium | Daichi Maruyama | 2026-04-28 | 2026-09-03 | Backlog | Pending external review
ITM-005 | Talent retention plan — top-200 roles | Issue | Low | Hadar Caspit | 2026-01-13 | 2026-06-18 | Blocked | Awaiting input from sponsor
ITM-006 | ESG disclosure — Scope 3 data quality | Decision | Low | Hadar Caspit | 2026-01-18 | 2026-07-01 | In progress | On track
ITM-007 | Cyber-resilience tabletop exercise | Issue | Medium | Sasha Ouellet | 2026-04-13 | 2026-08-05 | In progress | Awaiting input from sponsor
ITM-008 | Customer NPS recovery action | Risk | Low | Mod Admin | 2026-01-28 | 2026-10-24 | In progress | On track
ITM-009 | Working-capital DSO improvement | Decision | High | Hadar Caspit | 2026-03-01 | 2026-07-25 | In progress | Re-baselined this week
ITM-010 | Treasury hedge programme reset | Issue | Low | Hadar Caspit | 2026-01-25 | 2026-10-19 | Done | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Risk | Low | Mod Admin | 2026-05-12 | 2026-10-01 | In progress | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Issue | Low | Mod Admin | 2026-04-23 | 2026-10-10 | Backlog | Awaiting input from sponsor
ITM-013 | Inventory ABC re-segmentation | Decision | High | Sasha Ouellet | 2026-01-09 | 2026-07-19 | Done | Dependency cleared
ITM-014 | Procurement category sourcing wave | Decision | Low | Hadar Caspit | 2026-03-16 | 2026-08-22 | In progress | Dependency cleared
ITM-015 | Marketing campaign post-mortem | Action | High | Sasha Ouellet | 2026-03-04 | 2026-07-17 | Backlog | Pending external review
ITM-016 | IR investor day — readiness | Risk | Low | Daichi Maruyama | 2026-02-18 | 2026-11-17 | Blocked | On track
ITM-017 | Internal-audit annual plan refresh | Decision | Low | Mod Admin | 2026-02-11 | 2026-09-13 | Blocked | Dependency cleared
ITM-018 | ITGC remediation — access certification | Risk | Medium | Hadar Caspit | 2026-01-23 | 2026-06-26 | Blocked | Pending external review
ITM-019 | Health & Safety incident review | Action | Medium | Sasha Ouellet | 2026-03-12 | 2026-08-21 | Blocked | On track
ITM-020 | Data-quality master-data programme | Action | Low | Daichi Maruyama | 2026-02-24 | 2026-07-17 | Backlog | Awaiting input from sponsor
ITM-021 | Operating model — shared services design | Issue | Medium | Hadar Caspit | 2026-04-09 | 2026-08-01 | In progress | On track
ITM-022 | Legal — contract repository migration | Issue | High | Mod Admin | 2026-05-18 | 2026-07-07 | In progress | Pending external review
ITM-023 | Group strategy — refresh cadence | Decision | High | Hadar Caspit | 2026-05-14 | 2026-07-18 | In progress | Awaiting input from sponsor
ITM-024 | M&A pipeline triage | Decision | Low | Mod Admin | 2026-04-05 | 2026-10-25 | In progress | Pending external review
ITM-025 | Lender refinancing — Tranche A | Issue | Medium | Sasha Ouellet | 2026-04-28 | 2026-10-28 | Blocked | On track
ITM-026 | Tax compliance — transfer pricing | Issue | Medium | Hadar Caspit | 2026-03-04 | 2026-11-24 | Done | Pending external review
ITM-027 | Sustainability assurance scoping | Decision | Medium | Mod Admin | 2026-05-27 | 2026-07-12 | Backlog | Pending external review
ITM-028 | Customer-experience journey map refresh | Issue | High | Daichi Maruyama | 2026-04-22 | 2026-06-13 | Backlog | Dependency cleared
ITM-029 | Insurance renewal — directors & officers | Action | High | Hadar Caspit | 2026-05-28 | 2026-11-11 | Done | Re-baselined this week
ITM-030 | Risk appetite statement — refresh | Action | Low | Daichi Maruyama | 2026-01-11 | 2026-06-08 | In progress | Dependency cleared
ITM-031 | AI use-case prioritisation | Risk | Medium | Mod Admin | 2026-04-06 | 2026-08-19 | In progress | On track
ITM-032 | Procurement payment-terms harmonisation | Issue | High | Daichi Maruyama | 2026-05-16 | 2026-11-08 | Backlog | Awaiting input from sponsor