## Register
Compliance Register Live
Source file: Compliance_Register_Live.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Sasha Ouellet | 2026-02-24 | 2026-11-24 | Backlog | Dependency cleared
ITM-002 | Capex business case approval pending | Issue | High | Sasha Ouellet | 2026-04-20 | 2026-07-09 | Backlog | Pending external review
ITM-003 | Renewal of MSA — top 5 client | Risk | Low | Mod Admin | 2026-01-01 | 2026-09-15 | Blocked | On track
ITM-004 | S/4HANA cut-over readiness gap | Action | Medium | Sasha Ouellet | 2026-03-06 | 2026-11-09 | In progress | Awaiting input from sponsor
ITM-005 | Talent retention plan — top-200 roles | Action | Medium | Daichi Maruyama | 2026-04-03 | 2026-10-02 | Backlog | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Risk | Low | Sasha Ouellet | 2026-04-27 | 2026-08-18 | In progress | On track
ITM-007 | Cyber-resilience tabletop exercise | Issue | Medium | Hadar Caspit | 2026-02-20 | 2026-06-04 | Done | Pending external review
ITM-008 | Customer NPS recovery action | Risk | High | Mod Admin | 2026-04-12 | 2026-11-19 | In progress | Awaiting input from sponsor
ITM-009 | Working-capital DSO improvement | Risk | Low | Hadar Caspit | 2026-05-12 | 2026-09-15 | Done | On track
ITM-010 | Treasury hedge programme reset | Action | Low | Sasha Ouellet | 2026-05-09 | 2026-08-12 | Blocked | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Decision | Low | Mod Admin | 2026-01-22 | 2026-11-15 | Blocked | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Action | Medium | Sasha Ouellet | 2026-02-17 | 2026-09-12 | Backlog | Pending external review
ITM-013 | Inventory ABC re-segmentation | Action | Low | Mod Admin | 2026-05-13 | 2026-10-04 | Backlog | On track
ITM-014 | Procurement category sourcing wave | Decision | High | Daichi Maruyama | 2026-01-09 | 2026-08-02 | Backlog | Pending external review
ITM-015 | Marketing campaign post-mortem | Action | High | Daichi Maruyama | 2026-04-15 | 2026-11-27 | In progress | Re-baselined this week
ITM-016 | IR investor day — readiness | Risk | Medium | Daichi Maruyama | 2026-03-12 | 2026-07-12 | Backlog | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Action | Low | Hadar Caspit | 2026-01-07 | 2026-08-05 | Blocked | On track
ITM-018 | ITGC remediation — access certification | Decision | Low | Daichi Maruyama | 2026-01-08 | 2026-06-10 | Backlog | Awaiting input from sponsor
ITM-019 | Health & Safety incident review | Risk | Low | Mod Admin | 2026-05-04 | 2026-08-17 | In progress | Pending external review
ITM-020 | Data-quality master-data programme | Issue | High | Daichi Maruyama | 2026-03-10 | 2026-07-20 | In progress | Dependency cleared
ITM-021 | Operating model — shared services design | Issue | Medium | Mod Admin | 2026-05-26 | 2026-11-07 | Blocked | Pending external review
ITM-022 | Legal — contract repository migration | Action | High | Sasha Ouellet | 2026-03-24 | 2026-06-11 | Blocked | Re-baselined this week
ITM-023 | Group strategy — refresh cadence | Action | Medium | Sasha Ouellet | 2026-01-20 | 2026-08-25 | In progress | Re-baselined this week
ITM-024 | M&A pipeline triage | Issue | Medium | Hadar Caspit | 2026-02-18 | 2026-06-24 | Blocked | On track
ITM-025 | Lender refinancing — Tranche A | Action | Medium | Sasha Ouellet | 2026-03-28 | 2026-11-27 | Backlog | On track
ITM-026 | Tax compliance — transfer pricing | Issue | Medium | Mod Admin | 2026-01-26 | 2026-08-05 | In progress | Dependency cleared
ITM-027 | Sustainability assurance scoping | Action | Medium | Hadar Caspit | 2026-05-23 | 2026-07-13 | Backlog | Dependency cleared
ITM-028 | Customer-experience journey map refresh | Action | Low | Mod Admin | 2026-03-18 | 2026-11-06 | Blocked | Dependency cleared
ITM-029 | Insurance renewal — directors & officers | Action | Low | Hadar Caspit | 2026-02-21 | 2026-09-19 | Backlog | On track
ITM-030 | Risk appetite statement — refresh | Action | Low | Hadar Caspit | 2026-04-28 | 2026-08-11 | In progress | Re-baselined this week
ITM-031 | AI use-case prioritisation | Decision | Medium | Hadar Caspit | 2026-04-02 | 2026-10-17 | Blocked | On track
ITM-032 | Procurement payment-terms harmonisation | Issue | High | Sasha Ouellet | 2026-05-21 | 2026-10-03 | In progress | Re-baselined this week