## Register
ECM 01 GMV Cohort Tracker
Source file: ECM_01_GMV_Cohort_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Issue | Low | Daichi Maruyama | 2026-02-11 | 2026-09-26 | In progress | Re-baselined this week
ITM-002 | Capex business case approval pending | Decision | Medium | Hadar Caspit | 2026-04-14 | 2026-09-23 | Backlog | Awaiting input from sponsor
ITM-003 | Renewal of MSA — top 5 client | Risk | High | Hadar Caspit | 2026-04-26 | 2026-10-08 | In progress | Re-baselined this week
ITM-004 | S/4HANA cut-over readiness gap | Issue | Medium | Hadar Caspit | 2026-05-23 | 2026-07-07 | Done | On track
ITM-005 | Talent retention plan — top-200 roles | Risk | Low | Daichi Maruyama | 2026-02-02 | 2026-08-28 | Backlog | On track
ITM-006 | ESG disclosure — Scope 3 data quality | Issue | Medium | Mod Admin | 2026-04-12 | 2026-11-18 | Done | On track
ITM-007 | Cyber-resilience tabletop exercise | Decision | Low | Sasha Ouellet | 2026-01-19 | 2026-10-02 | In progress | On track
ITM-008 | Customer NPS recovery action | Decision | Medium | Daichi Maruyama | 2026-03-09 | 2026-06-08 | In progress | Awaiting input from sponsor
ITM-009 | Working-capital DSO improvement | Risk | Medium | Hadar Caspit | 2026-01-02 | 2026-06-22 | Done | Pending external review
ITM-010 | Treasury hedge programme reset | Issue | Medium | Mod Admin | 2026-03-10 | 2026-06-23 | Blocked | Dependency cleared
ITM-011 | Board-paper template refresh | Risk | Medium | Hadar Caspit | 2026-03-07 | 2026-07-16 | Done | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Decision | Medium | Sasha Ouellet | 2026-03-26 | 2026-09-12 | In progress | On track
ITM-013 | Inventory ABC re-segmentation | Decision | Low | Sasha Ouellet | 2026-02-01 | 2026-11-13 | In progress | Pending external review
ITM-014 | Procurement category sourcing wave | Decision | Low | Mod Admin | 2026-03-20 | 2026-06-20 | In progress | Awaiting input from sponsor
ITM-015 | Marketing campaign post-mortem | Issue | Medium | Daichi Maruyama | 2026-01-17 | 2026-10-02 | In progress | Pending external review
ITM-016 | IR investor day — readiness | Issue | Medium | Sasha Ouellet | 2026-01-12 | 2026-11-15 | Done | Dependency cleared
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Mod Admin | 2026-03-16 | 2026-08-09 | Done | On track
ITM-018 | ITGC remediation — access certification | Decision | High | Daichi Maruyama | 2026-01-18 | 2026-11-18 | In progress | Dependency cleared
ITM-019 | Health & Safety incident review | Action | Medium | Hadar Caspit | 2026-04-11 | 2026-11-12 | Blocked | On track
ITM-020 | Data-quality master-data programme | Risk | Low | Daichi Maruyama | 2026-05-09 | 2026-11-05 | Backlog | Dependency cleared
ITM-021 | Operating model — shared services design | Decision | High | Mod Admin | 2026-05-12 | 2026-11-11 | Done | Re-baselined this week
ITM-022 | Legal — contract repository migration | Risk | Medium | Sasha Ouellet | 2026-02-16 | 2026-11-01 | Blocked | Dependency cleared
ITM-023 | Group strategy — refresh cadence | Risk | Low | Sasha Ouellet | 2026-02-20 | 2026-10-04 | Done | Dependency cleared
ITM-024 | M&A pipeline triage | Issue | Low | Hadar Caspit | 2026-02-04 | 2026-11-07 | In progress | Pending external review
ITM-025 | Lender refinancing — Tranche A | Action | Medium | Sasha Ouellet | 2026-02-19 | 2026-11-11 | Backlog | On track
ITM-026 | Tax compliance — transfer pricing | Decision | Medium | Hadar Caspit | 2026-03-25 | 2026-08-15 | Backlog | Awaiting input from sponsor
ITM-027 | Sustainability assurance scoping | Issue | High | Hadar Caspit | 2026-04-01 | 2026-11-04 | Blocked | Awaiting input from sponsor
ITM-028 | Customer-experience journey map refresh | Issue | Low | Daichi Maruyama | 2026-03-27 | 2026-07-03 | In progress | Pending external review
ITM-029 | Insurance renewal — directors & officers | Decision | High | Sasha Ouellet | 2026-03-28 | 2026-09-12 | Done | On track
ITM-030 | Risk appetite statement — refresh | Issue | Low | Mod Admin | 2026-01-28 | 2026-06-26 | Blocked | Pending external review
ITM-031 | AI use-case prioritisation | Issue | Low | Mod Admin | 2026-02-05 | 2026-06-12 | In progress | Dependency cleared
ITM-032 | Procurement payment-terms harmonisation | Action | Low | Mod Admin | 2026-03-06 | 2026-06-11 | Blocked | Dependency cleared