## Register
GOV PQ Tracker
Source file: GOV_PQ_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Low | Hadar Caspit | 2026-05-22 | 2026-06-11 | Blocked | On track
ITM-002 | Capex business case approval pending | Risk | High | Mod Admin | 2026-02-12 | 2026-11-05 | Done | On track
ITM-003 | Renewal of MSA — top 5 client | Action | Medium | Hadar Caspit | 2026-05-04 | 2026-06-10 | Blocked | On track
ITM-004 | S/4HANA cut-over readiness gap | Risk | Medium | Hadar Caspit | 2026-05-13 | 2026-09-17 | In progress | Awaiting input from sponsor
ITM-005 | Talent retention plan — top-200 roles | Action | Low | Sasha Ouellet | 2026-01-15 | 2026-10-24 | Blocked | Dependency cleared
ITM-006 | ESG disclosure — Scope 3 data quality | Decision | Medium | Sasha Ouellet | 2026-03-06 | 2026-11-14 | In progress | Dependency cleared
ITM-007 | Cyber-resilience tabletop exercise | Issue | Medium | Daichi Maruyama | 2026-05-02 | 2026-06-11 | Backlog | Re-baselined this week
ITM-008 | Customer NPS recovery action | Issue | Low | Mod Admin | 2026-01-02 | 2026-08-02 | Backlog | Re-baselined this week
ITM-009 | Working-capital DSO improvement | Risk | Low | Mod Admin | 2026-01-15 | 2026-09-09 | In progress | Pending external review
ITM-010 | Treasury hedge programme reset | Decision | Low | Mod Admin | 2026-01-20 | 2026-10-16 | Blocked | On track
ITM-011 | Board-paper template refresh | Risk | Medium | Daichi Maruyama | 2026-03-22 | 2026-07-28 | Backlog | Re-baselined this week
ITM-012 | Whistleblowing case — investigation | Action | High | Sasha Ouellet | 2026-04-05 | 2026-11-09 | Backlog | Dependency cleared
ITM-013 | Inventory ABC re-segmentation | Action | Low | Hadar Caspit | 2026-01-27 | 2026-11-26 | Done | On track
ITM-014 | Procurement category sourcing wave | Action | Medium | Daichi Maruyama | 2026-04-05 | 2026-06-07 | Backlog | On track
ITM-015 | Marketing campaign post-mortem | Issue | Medium | Mod Admin | 2026-03-11 | 2026-10-14 | Backlog | Re-baselined this week
ITM-016 | IR investor day — readiness | Issue | Low | Hadar Caspit | 2026-01-27 | 2026-09-21 | In progress | On track
ITM-017 | Internal-audit annual plan refresh | Issue | Medium | Sasha Ouellet | 2026-04-07 | 2026-10-24 | Blocked | On track
ITM-018 | ITGC remediation — access certification | Action | Medium | Hadar Caspit | 2026-05-16 | 2026-06-05 | In progress | On track
ITM-019 | Health & Safety incident review | Decision | Low | Hadar Caspit | 2026-03-16 | 2026-06-13 | In progress | On track
ITM-020 | Data-quality master-data programme | Action | Low | Sasha Ouellet | 2026-05-05 | 2026-06-05 | Blocked | On track
ITM-021 | Operating model — shared services design | Action | Medium | Mod Admin | 2026-02-16 | 2026-11-14 | Done | On track
ITM-022 | Legal — contract repository migration | Issue | Medium | Sasha Ouellet | 2026-04-21 | 2026-06-23 | Blocked | Pending external review
ITM-023 | Group strategy — refresh cadence | Action | Medium | Sasha Ouellet | 2026-03-16 | 2026-10-10 | In progress | Dependency cleared
ITM-024 | M&A pipeline triage | Action | Low | Hadar Caspit | 2026-01-14 | 2026-09-25 | In progress | Dependency cleared
ITM-025 | Lender refinancing — Tranche A | Action | Medium | Hadar Caspit | 2026-03-25 | 2026-09-12 | Backlog | On track
ITM-026 | Tax compliance — transfer pricing | Risk | High | Sasha Ouellet | 2026-03-18 | 2026-09-20 | In progress | Awaiting input from sponsor
ITM-027 | Sustainability assurance scoping | Action | Medium | Mod Admin | 2026-01-13 | 2026-11-22 | In progress | Awaiting input from sponsor
ITM-028 | Customer-experience journey map refresh | Decision | Low | Daichi Maruyama | 2026-03-12 | 2026-07-05 | In progress | Pending external review
ITM-029 | Insurance renewal — directors & officers | Action | Medium | Mod Admin | 2026-02-25 | 2026-11-17 | In progress | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Issue | High | Daichi Maruyama | 2026-03-06 | 2026-09-12 | Done | Re-baselined this week
ITM-031 | AI use-case prioritisation | Action | Low | Sasha Ouellet | 2026-01-14 | 2026-06-16 | In progress | Re-baselined this week
ITM-032 | Procurement payment-terms harmonisation | Issue | Low | Mod Admin | 2026-04-07 | 2026-09-18 | In progress | On track