## Register
ISL 04 GIA Performance Tracker
Source file: ISL_04_GIA_Performance_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Mod Admin | 2026-04-21 | 2026-06-23 | In progress | Re-baselined this week
ITM-002 | Capex business case approval pending | Risk | Low | Hadar Caspit | 2026-05-28 | 2026-08-12 | In progress | Awaiting input from sponsor
ITM-003 | Renewal of MSA — top 5 client | Issue | Medium | Mod Admin | 2026-04-27 | 2026-11-26 | In progress | Re-baselined this week
ITM-004 | S/4HANA cut-over readiness gap | Issue | Medium | Mod Admin | 2026-03-01 | 2026-11-14 | In progress | Re-baselined this week
ITM-005 | Talent retention plan — top-200 roles | Issue | Low | Sasha Ouellet | 2026-02-06 | 2026-11-14 | In progress | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Risk | Low | Daichi Maruyama | 2026-04-28 | 2026-06-05 | Blocked | Dependency cleared
ITM-007 | Cyber-resilience tabletop exercise | Decision | High | Daichi Maruyama | 2026-05-14 | 2026-11-28 | Done | Dependency cleared
ITM-008 | Customer NPS recovery action | Risk | Low | Sasha Ouellet | 2026-04-17 | 2026-08-19 | In progress | Re-baselined this week
ITM-009 | Working-capital DSO improvement | Risk | Low | Daichi Maruyama | 2026-05-06 | 2026-08-01 | Done | On track
ITM-010 | Treasury hedge programme reset | Issue | Medium | Hadar Caspit | 2026-03-12 | 2026-06-01 | Backlog | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Action | Medium | Daichi Maruyama | 2026-01-06 | 2026-10-06 | Done | Pending external review
ITM-012 | Whistleblowing case — investigation | Risk | Medium | Sasha Ouellet | 2026-03-02 | 2026-06-08 | In progress | Re-baselined this week
ITM-013 | Inventory ABC re-segmentation | Action | Low | Mod Admin | 2026-01-24 | 2026-10-05 | Blocked | On track
ITM-014 | Procurement category sourcing wave | Decision | High | Hadar Caspit | 2026-03-14 | 2026-06-14 | Done | Dependency cleared
ITM-015 | Marketing campaign post-mortem | Decision | Low | Daichi Maruyama | 2026-04-19 | 2026-09-02 | In progress | Dependency cleared
ITM-016 | IR investor day — readiness | Decision | Medium | Sasha Ouellet | 2026-02-17 | 2026-11-07 | In progress | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Action | Low | Daichi Maruyama | 2026-05-27 | 2026-08-24 | Backlog | Dependency cleared
ITM-018 | ITGC remediation — access certification | Risk | Low | Mod Admin | 2026-04-08 | 2026-11-04 | Blocked | Re-baselined this week
ITM-019 | Health & Safety incident review | Risk | Medium | Hadar Caspit | 2026-05-13 | 2026-06-13 | Backlog | Pending external review
ITM-020 | Data-quality master-data programme | Action | High | Mod Admin | 2026-04-17 | 2026-10-28 | Backlog | On track
ITM-021 | Operating model — shared services design | Issue | Medium | Daichi Maruyama | 2026-05-11 | 2026-07-24 | In progress | Pending external review
ITM-022 | Legal — contract repository migration | Issue | Low | Mod Admin | 2026-03-14 | 2026-06-08 | In progress | Dependency cleared
ITM-023 | Group strategy — refresh cadence | Risk | Low | Daichi Maruyama | 2026-01-10 | 2026-08-27 | In progress | Dependency cleared
ITM-024 | M&A pipeline triage | Action | Medium | Hadar Caspit | 2026-01-27 | 2026-10-03 | Backlog | Pending external review
ITM-025 | Lender refinancing — Tranche A | Decision | Low | Sasha Ouellet | 2026-02-01 | 2026-07-11 | Blocked | Awaiting input from sponsor
ITM-026 | Tax compliance — transfer pricing | Action | Low | Hadar Caspit | 2026-02-25 | 2026-10-19 | In progress | Dependency cleared
ITM-027 | Sustainability assurance scoping | Action | Medium | Mod Admin | 2026-01-17 | 2026-11-19 | In progress | On track
ITM-028 | Customer-experience journey map refresh | Risk | Medium | Mod Admin | 2026-05-07 | 2026-10-15 | In progress | Pending external review
ITM-029 | Insurance renewal — directors & officers | Action | Medium | Mod Admin | 2026-03-07 | 2026-10-25 | Blocked | On track
ITM-030 | Risk appetite statement — refresh | Risk | Medium | Sasha Ouellet | 2026-01-17 | 2026-10-22 | In progress | On track
ITM-031 | AI use-case prioritisation | Risk | Medium | Mod Admin | 2026-03-03 | 2026-06-27 | Backlog | Re-baselined this week
ITM-032 | Procurement payment-terms harmonisation | Risk | Low | Hadar Caspit | 2026-04-27 | 2026-08-18 | Backlog | Pending external review