## Register
IT 01 Transformation Tracker
Source file: IT_01_Transformation_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Sasha Ouellet | 2026-05-13 | 2026-06-28 | Backlog | Re-baselined this week
ITM-002 | Capex business case approval pending | Risk | Medium | Sasha Ouellet | 2026-01-04 | 2026-09-25 | Done | Pending external review
ITM-003 | Renewal of MSA — top 5 client | Risk | High | Daichi Maruyama | 2026-03-08 | 2026-06-10 | In progress | Dependency cleared
ITM-004 | S/4HANA cut-over readiness gap | Decision | High | Daichi Maruyama | 2026-03-18 | 2026-10-03 | In progress | Dependency cleared
ITM-005 | Talent retention plan — top-200 roles | Issue | Low | Mod Admin | 2026-01-12 | 2026-06-10 | Blocked | On track
ITM-006 | ESG disclosure — Scope 3 data quality | Decision | Medium | Sasha Ouellet | 2026-02-19 | 2026-07-18 | Done | Awaiting input from sponsor
ITM-007 | Cyber-resilience tabletop exercise | Issue | Low | Sasha Ouellet | 2026-05-02 | 2026-11-03 | Backlog | Re-baselined this week
ITM-008 | Customer NPS recovery action | Action | Medium | Mod Admin | 2026-03-02 | 2026-10-19 | In progress | On track
ITM-009 | Working-capital DSO improvement | Issue | Medium | Sasha Ouellet | 2026-01-25 | 2026-08-08 | In progress | Awaiting input from sponsor
ITM-010 | Treasury hedge programme reset | Risk | Low | Hadar Caspit | 2026-05-03 | 2026-09-14 | In progress | Dependency cleared
ITM-011 | Board-paper template refresh | Decision | Low | Sasha Ouellet | 2026-02-10 | 2026-07-10 | Backlog | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Action | High | Daichi Maruyama | 2026-03-17 | 2026-06-17 | Done | Dependency cleared
ITM-013 | Inventory ABC re-segmentation | Decision | Low | Sasha Ouellet | 2026-03-28 | 2026-07-27 | Done | Pending external review
ITM-014 | Procurement category sourcing wave | Action | Low | Daichi Maruyama | 2026-02-01 | 2026-06-23 | Done | Dependency cleared
ITM-015 | Marketing campaign post-mortem | Action | Medium | Sasha Ouellet | 2026-05-20 | 2026-06-26 | Done | Re-baselined this week
ITM-016 | IR investor day — readiness | Risk | Medium | Mod Admin | 2026-04-28 | 2026-08-20 | Backlog | Pending external review
ITM-017 | Internal-audit annual plan refresh | Issue | Low | Mod Admin | 2026-04-14 | 2026-11-10 | Done | Awaiting input from sponsor
ITM-018 | ITGC remediation — access certification | Action | Medium | Hadar Caspit | 2026-01-13 | 2026-10-25 | In progress | Awaiting input from sponsor
ITM-019 | Health & Safety incident review | Action | Medium | Hadar Caspit | 2026-01-07 | 2026-08-13 | In progress | Awaiting input from sponsor
ITM-020 | Data-quality master-data programme | Issue | Medium | Daichi Maruyama | 2026-03-09 | 2026-11-04 | In progress | Awaiting input from sponsor
ITM-021 | Operating model — shared services design | Issue | Medium | Sasha Ouellet | 2026-05-12 | 2026-07-21 | In progress | Pending external review
ITM-022 | Legal — contract repository migration | Risk | High | Sasha Ouellet | 2026-03-15 | 2026-06-25 | In progress | Dependency cleared
ITM-023 | Group strategy — refresh cadence | Decision | Medium | Mod Admin | 2026-05-10 | 2026-10-16 | Backlog | Awaiting input from sponsor
ITM-024 | M&A pipeline triage | Risk | High | Sasha Ouellet | 2026-04-09 | 2026-10-15 | Blocked | On track
ITM-025 | Lender refinancing — Tranche A | Action | Medium | Daichi Maruyama | 2026-02-19 | 2026-07-24 | Blocked | Dependency cleared
ITM-026 | Tax compliance — transfer pricing | Action | Medium | Hadar Caspit | 2026-04-15 | 2026-07-07 | Done | Awaiting input from sponsor
ITM-027 | Sustainability assurance scoping | Issue | High | Mod Admin | 2026-05-14 | 2026-08-23 | Backlog | On track
ITM-028 | Customer-experience journey map refresh | Issue | Low | Hadar Caspit | 2026-02-28 | 2026-11-27 | Done | Re-baselined this week
ITM-029 | Insurance renewal — directors & officers | Risk | Low | Sasha Ouellet | 2026-05-09 | 2026-11-18 | Done | On track
ITM-030 | Risk appetite statement — refresh | Issue | Low | Sasha Ouellet | 2026-04-08 | 2026-07-13 | In progress | Awaiting input from sponsor
ITM-031 | AI use-case prioritisation | Action | Medium | Sasha Ouellet | 2026-03-15 | 2026-08-14 | Done | Dependency cleared
ITM-032 | Procurement payment-terms harmonisation | Risk | Medium | Sasha Ouellet | 2026-05-15 | 2026-08-07 | In progress | On track