## Register
MFG 05 Customer OTIF Tracker
Source file: MFG_05_Customer_OTIF_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Issue | Low | Mod Admin | 2026-04-23 | 2026-07-19 | In progress | Re-baselined this week
ITM-002 | Capex business case approval pending | Risk | Medium | Mod Admin | 2026-04-14 | 2026-08-10 | Backlog | Re-baselined this week
ITM-003 | Renewal of MSA — top 5 client | Risk | Medium | Mod Admin | 2026-04-22 | 2026-07-21 | In progress | On track
ITM-004 | S/4HANA cut-over readiness gap | Risk | Medium | Sasha Ouellet | 2026-03-07 | 2026-11-05 | Backlog | Awaiting input from sponsor
ITM-005 | Talent retention plan — top-200 roles | Decision | Medium | Daichi Maruyama | 2026-04-28 | 2026-11-22 | Done | Re-baselined this week
ITM-006 | ESG disclosure — Scope 3 data quality | Issue | Medium | Hadar Caspit | 2026-01-25 | 2026-06-07 | Backlog | Awaiting input from sponsor
ITM-007 | Cyber-resilience tabletop exercise | Action | Medium | Hadar Caspit | 2026-01-19 | 2026-07-27 | In progress | On track
ITM-008 | Customer NPS recovery action | Risk | Low | Hadar Caspit | 2026-01-10 | 2026-06-05 | In progress | Pending external review
ITM-009 | Working-capital DSO improvement | Decision | Low | Daichi Maruyama | 2026-04-12 | 2026-11-03 | In progress | Dependency cleared
ITM-010 | Treasury hedge programme reset | Risk | Medium | Hadar Caspit | 2026-04-01 | 2026-08-03 | In progress | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Action | Medium | Hadar Caspit | 2026-05-18 | 2026-07-06 | In progress | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Action | Medium | Hadar Caspit | 2026-02-03 | 2026-07-13 | Done | Awaiting input from sponsor
ITM-013 | Inventory ABC re-segmentation | Issue | High | Hadar Caspit | 2026-01-07 | 2026-09-08 | In progress | Dependency cleared
ITM-014 | Procurement category sourcing wave | Action | Low | Mod Admin | 2026-04-04 | 2026-08-05 | In progress | Awaiting input from sponsor
ITM-015 | Marketing campaign post-mortem | Issue | Medium | Mod Admin | 2026-02-26 | 2026-07-24 | Blocked | Re-baselined this week
ITM-016 | IR investor day — readiness | Risk | Medium | Hadar Caspit | 2026-05-21 | 2026-06-16 | In progress | Pending external review
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Hadar Caspit | 2026-05-18 | 2026-07-13 | In progress | Dependency cleared
ITM-018 | ITGC remediation — access certification | Issue | High | Mod Admin | 2026-05-01 | 2026-06-01 | In progress | Awaiting input from sponsor
ITM-019 | Health & Safety incident review | Issue | Medium | Daichi Maruyama | 2026-05-08 | 2026-07-27 | Blocked | Dependency cleared
ITM-020 | Data-quality master-data programme | Action | Medium | Mod Admin | 2026-05-07 | 2026-11-18 | Backlog | On track
ITM-021 | Operating model — shared services design | Issue | Medium | Daichi Maruyama | 2026-01-10 | 2026-06-24 | Backlog | Awaiting input from sponsor
ITM-022 | Legal — contract repository migration | Action | Medium | Mod Admin | 2026-04-08 | 2026-08-15 | Blocked | Awaiting input from sponsor
ITM-023 | Group strategy — refresh cadence | Decision | Medium | Sasha Ouellet | 2026-03-17 | 2026-06-03 | Done | On track
ITM-024 | M&A pipeline triage | Risk | Medium | Daichi Maruyama | 2026-02-17 | 2026-09-18 | In progress | On track
ITM-025 | Lender refinancing — Tranche A | Risk | High | Mod Admin | 2026-03-19 | 2026-07-25 | Done | Re-baselined this week
ITM-026 | Tax compliance — transfer pricing | Issue | Medium | Daichi Maruyama | 2026-04-16 | 2026-06-20 | Backlog | Dependency cleared
ITM-027 | Sustainability assurance scoping | Issue | High | Daichi Maruyama | 2026-03-23 | 2026-09-07 | Blocked | On track
ITM-028 | Customer-experience journey map refresh | Decision | Medium | Daichi Maruyama | 2026-03-01 | 2026-06-23 | Done | Awaiting input from sponsor
ITM-029 | Insurance renewal — directors & officers | Action | Low | Sasha Ouellet | 2026-05-24 | 2026-11-07 | Blocked | Re-baselined this week
ITM-030 | Risk appetite statement — refresh | Action | Low | Daichi Maruyama | 2026-04-03 | 2026-09-05 | In progress | Re-baselined this week
ITM-031 | AI use-case prioritisation | Risk | Low | Mod Admin | 2026-04-05 | 2026-11-14 | Done | Awaiting input from sponsor
ITM-032 | Procurement payment-terms harmonisation | Action | High | Daichi Maruyama | 2026-05-26 | 2026-10-09 | In progress | Re-baselined this week