## Register
Network Recovery Tracker
Source file: Network_Recovery_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Sasha Ouellet | 2026-03-09 | 2026-11-03 | Backlog | Pending external review
ITM-002 | Capex business case approval pending | Decision | Medium | Sasha Ouellet | 2026-01-14 | 2026-09-03 | In progress | Awaiting input from sponsor
ITM-003 | Renewal of MSA — top 5 client | Action | Low | Sasha Ouellet | 2026-04-22 | 2026-06-16 | Backlog | Awaiting input from sponsor
ITM-004 | S/4HANA cut-over readiness gap | Decision | Low | Hadar Caspit | 2026-01-01 | 2026-08-23 | Blocked | Pending external review
ITM-005 | Talent retention plan — top-200 roles | Action | Low | Daichi Maruyama | 2026-03-14 | 2026-06-22 | In progress | Re-baselined this week
ITM-006 | ESG disclosure — Scope 3 data quality | Risk | Low | Mod Admin | 2026-01-27 | 2026-07-26 | Backlog | Pending external review
ITM-007 | Cyber-resilience tabletop exercise | Issue | High | Sasha Ouellet | 2026-04-20 | 2026-10-18 | In progress | Awaiting input from sponsor
ITM-008 | Customer NPS recovery action | Action | Medium | Hadar Caspit | 2026-05-28 | 2026-08-10 | In progress | Dependency cleared
ITM-009 | Working-capital DSO improvement | Decision | Medium | Daichi Maruyama | 2026-01-28 | 2026-11-08 | Done | On track
ITM-010 | Treasury hedge programme reset | Action | High | Sasha Ouellet | 2026-03-01 | 2026-06-22 | In progress | Dependency cleared
ITM-011 | Board-paper template refresh | Risk | Medium | Daichi Maruyama | 2026-05-10 | 2026-09-23 | In progress | Re-baselined this week
ITM-012 | Whistleblowing case — investigation | Decision | Low | Hadar Caspit | 2026-03-20 | 2026-09-28 | Backlog | Awaiting input from sponsor
ITM-013 | Inventory ABC re-segmentation | Action | Low | Sasha Ouellet | 2026-04-06 | 2026-07-07 | Backlog | Re-baselined this week
ITM-014 | Procurement category sourcing wave | Risk | Low | Sasha Ouellet | 2026-03-24 | 2026-06-26 | Backlog | On track
ITM-015 | Marketing campaign post-mortem | Issue | Low | Sasha Ouellet | 2026-03-14 | 2026-10-04 | Done | Dependency cleared
ITM-016 | IR investor day — readiness | Decision | Medium | Daichi Maruyama | 2026-04-24 | 2026-11-28 | In progress | Re-baselined this week
ITM-017 | Internal-audit annual plan refresh | Risk | High | Mod Admin | 2026-02-16 | 2026-08-26 | In progress | Awaiting input from sponsor
ITM-018 | ITGC remediation — access certification | Decision | Low | Mod Admin | 2026-05-26 | 2026-09-02 | Backlog | Pending external review
ITM-019 | Health & Safety incident review | Issue | High | Mod Admin | 2026-03-26 | 2026-11-22 | In progress | Awaiting input from sponsor
ITM-020 | Data-quality master-data programme | Issue | Medium | Sasha Ouellet | 2026-02-03 | 2026-10-24 | Done | Pending external review
ITM-021 | Operating model — shared services design | Action | Low | Mod Admin | 2026-03-11 | 2026-08-01 | In progress | Dependency cleared
ITM-022 | Legal — contract repository migration | Action | High | Hadar Caspit | 2026-01-03 | 2026-07-07 | Done | Pending external review
ITM-023 | Group strategy — refresh cadence | Action | Medium | Mod Admin | 2026-01-10 | 2026-10-09 | Backlog | Pending external review
ITM-024 | M&A pipeline triage | Issue | High | Sasha Ouellet | 2026-04-10 | 2026-11-07 | Blocked | On track
ITM-025 | Lender refinancing — Tranche A | Risk | Low | Daichi Maruyama | 2026-04-07 | 2026-11-03 | In progress | Re-baselined this week
ITM-026 | Tax compliance — transfer pricing | Decision | Medium | Hadar Caspit | 2026-04-11 | 2026-11-08 | In progress | Dependency cleared
ITM-027 | Sustainability assurance scoping | Action | Low | Sasha Ouellet | 2026-04-15 | 2026-07-26 | In progress | On track
ITM-028 | Customer-experience journey map refresh | Action | Medium | Sasha Ouellet | 2026-03-22 | 2026-08-14 | In progress | Re-baselined this week
ITM-029 | Insurance renewal — directors & officers | Risk | Low | Hadar Caspit | 2026-04-03 | 2026-07-18 | Backlog | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Risk | Low | Sasha Ouellet | 2026-05-13 | 2026-08-14 | Blocked | Pending external review
ITM-031 | AI use-case prioritisation | Risk | Low | Daichi Maruyama | 2026-02-16 | 2026-10-25 | Done | Dependency cleared
ITM-032 | Procurement payment-terms harmonisation | Risk | Medium | Hadar Caspit | 2026-04-10 | 2026-11-28 | In progress | Pending external review