## Register
PROC 02 Vendor Consolidation Tracker
Source file: PROC_02_Vendor_Consolidation_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Hadar Caspit | 2026-03-01 | 2026-11-20 | In progress | Dependency cleared
ITM-002 | Capex business case approval pending | Action | High | Sasha Ouellet | 2026-03-11 | 2026-09-15 | Backlog | Dependency cleared
ITM-003 | Renewal of MSA — top 5 client | Action | Low | Daichi Maruyama | 2026-05-24 | 2026-06-05 | Done | Pending external review
ITM-004 | S/4HANA cut-over readiness gap | Issue | High | Sasha Ouellet | 2026-01-14 | 2026-09-18 | Blocked | Dependency cleared
ITM-005 | Talent retention plan — top-200 roles | Decision | Low | Mod Admin | 2026-05-26 | 2026-06-20 | Blocked | Dependency cleared
ITM-006 | ESG disclosure — Scope 3 data quality | Action | Medium | Daichi Maruyama | 2026-01-21 | 2026-08-28 | In progress | Pending external review
ITM-007 | Cyber-resilience tabletop exercise | Action | Medium | Sasha Ouellet | 2026-05-17 | 2026-06-17 | Blocked | Awaiting input from sponsor
ITM-008 | Customer NPS recovery action | Action | Medium | Hadar Caspit | 2026-02-28 | 2026-11-05 | Done | Dependency cleared
ITM-009 | Working-capital DSO improvement | Risk | High | Sasha Ouellet | 2026-03-23 | 2026-08-19 | Backlog | Awaiting input from sponsor
ITM-010 | Treasury hedge programme reset | Issue | Medium | Hadar Caspit | 2026-03-28 | 2026-11-12 | In progress | Pending external review
ITM-011 | Board-paper template refresh | Issue | Medium | Daichi Maruyama | 2026-02-03 | 2026-09-18 | Backlog | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Action | Low | Daichi Maruyama | 2026-04-16 | 2026-10-22 | In progress | Re-baselined this week
ITM-013 | Inventory ABC re-segmentation | Action | Low | Sasha Ouellet | 2026-04-28 | 2026-07-05 | Done | On track
ITM-014 | Procurement category sourcing wave | Action | Medium | Mod Admin | 2026-03-23 | 2026-08-05 | Backlog | Pending external review
ITM-015 | Marketing campaign post-mortem | Decision | Low | Sasha Ouellet | 2026-01-07 | 2026-09-10 | In progress | Awaiting input from sponsor
ITM-016 | IR investor day — readiness | Decision | High | Hadar Caspit | 2026-01-11 | 2026-08-22 | Done | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Risk | Low | Mod Admin | 2026-01-22 | 2026-09-09 | Backlog | Pending external review
ITM-018 | ITGC remediation — access certification | Action | Medium | Daichi Maruyama | 2026-05-08 | 2026-08-03 | In progress | Dependency cleared
ITM-019 | Health & Safety incident review | Issue | Low | Hadar Caspit | 2026-04-12 | 2026-06-15 | In progress | Pending external review
ITM-020 | Data-quality master-data programme | Issue | High | Hadar Caspit | 2026-04-26 | 2026-08-01 | Done | On track
ITM-021 | Operating model — shared services design | Decision | Low | Sasha Ouellet | 2026-04-25 | 2026-06-04 | Blocked | Dependency cleared
ITM-022 | Legal — contract repository migration | Action | Medium | Mod Admin | 2026-01-14 | 2026-08-01 | Blocked | Pending external review
ITM-023 | Group strategy — refresh cadence | Decision | High | Mod Admin | 2026-04-19 | 2026-06-20 | Blocked | Awaiting input from sponsor
ITM-024 | M&A pipeline triage | Action | Low | Daichi Maruyama | 2026-02-18 | 2026-07-23 | Done | Awaiting input from sponsor
ITM-025 | Lender refinancing — Tranche A | Action | Low | Sasha Ouellet | 2026-03-05 | 2026-08-23 | In progress | Pending external review
ITM-026 | Tax compliance — transfer pricing | Decision | Low | Mod Admin | 2026-03-03 | 2026-10-01 | Done | On track
ITM-027 | Sustainability assurance scoping | Risk | Low | Mod Admin | 2026-04-06 | 2026-11-24 | Done | On track
ITM-028 | Customer-experience journey map refresh | Issue | Medium | Daichi Maruyama | 2026-04-23 | 2026-08-03 | Done | Re-baselined this week
ITM-029 | Insurance renewal — directors & officers | Issue | High | Daichi Maruyama | 2026-03-07 | 2026-08-18 | Done | Pending external review
ITM-030 | Risk appetite statement — refresh | Decision | Medium | Hadar Caspit | 2026-05-18 | 2026-06-04 | In progress | Pending external review
ITM-031 | AI use-case prioritisation | Action | Low | Mod Admin | 2026-05-24 | 2026-11-01 | In progress | Pending external review
ITM-032 | Procurement payment-terms harmonisation | Issue | Low | Hadar Caspit | 2026-04-14 | 2026-10-17 | Done | Re-baselined this week