## Register
PROP 04 Mall Tenancy Tracker
Source file: PROP_04_Mall_Tenancy_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Decision | Low | Sasha Ouellet | 2026-05-06 | 2026-06-05 | In progress | Re-baselined this week
ITM-002 | Capex business case approval pending | Issue | Low | Daichi Maruyama | 2026-02-23 | 2026-09-15 | In progress | Dependency cleared
ITM-003 | Renewal of MSA — top 5 client | Decision | High | Daichi Maruyama | 2026-02-18 | 2026-07-07 | Done | Awaiting input from sponsor
ITM-004 | S/4HANA cut-over readiness gap | Decision | Medium | Daichi Maruyama | 2026-01-09 | 2026-10-07 | In progress | Dependency cleared
ITM-005 | Talent retention plan — top-200 roles | Issue | High | Mod Admin | 2026-02-16 | 2026-07-04 | Blocked | Awaiting input from sponsor
ITM-006 | ESG disclosure — Scope 3 data quality | Issue | Medium | Mod Admin | 2026-05-06 | 2026-11-18 | Backlog | On track
ITM-007 | Cyber-resilience tabletop exercise | Action | Low | Sasha Ouellet | 2026-02-02 | 2026-10-22 | In progress | Pending external review
ITM-008 | Customer NPS recovery action | Decision | Medium | Daichi Maruyama | 2026-03-01 | 2026-09-03 | Blocked | On track
ITM-009 | Working-capital DSO improvement | Decision | Medium | Sasha Ouellet | 2026-05-24 | 2026-06-25 | In progress | Awaiting input from sponsor
ITM-010 | Treasury hedge programme reset | Action | Low | Daichi Maruyama | 2026-05-16 | 2026-06-14 | Done | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Issue | Low | Daichi Maruyama | 2026-02-02 | 2026-10-25 | Backlog | Re-baselined this week
ITM-012 | Whistleblowing case — investigation | Risk | Low | Daichi Maruyama | 2026-05-22 | 2026-10-19 | Blocked | Awaiting input from sponsor
ITM-013 | Inventory ABC re-segmentation | Decision | Low | Hadar Caspit | 2026-01-13 | 2026-09-24 | In progress | Re-baselined this week
ITM-014 | Procurement category sourcing wave | Issue | Low | Daichi Maruyama | 2026-02-01 | 2026-09-07 | Blocked | Re-baselined this week
ITM-015 | Marketing campaign post-mortem | Action | Low | Sasha Ouellet | 2026-01-03 | 2026-09-24 | In progress | On track
ITM-016 | IR investor day — readiness | Decision | Low | Sasha Ouellet | 2026-04-28 | 2026-10-13 | Backlog | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Sasha Ouellet | 2026-04-11 | 2026-07-19 | Backlog | On track
ITM-018 | ITGC remediation — access certification | Risk | Low | Sasha Ouellet | 2026-04-18 | 2026-06-20 | In progress | Re-baselined this week
ITM-019 | Health & Safety incident review | Action | Low | Hadar Caspit | 2026-03-10 | 2026-07-05 | Blocked | Pending external review
ITM-020 | Data-quality master-data programme | Issue | High | Hadar Caspit | 2026-02-13 | 2026-09-06 | Blocked | Re-baselined this week
ITM-021 | Operating model — shared services design | Action | High | Sasha Ouellet | 2026-02-27 | 2026-08-24 | Backlog | On track
ITM-022 | Legal — contract repository migration | Risk | Low | Mod Admin | 2026-05-14 | 2026-07-26 | Done | Awaiting input from sponsor
ITM-023 | Group strategy — refresh cadence | Risk | Low | Mod Admin | 2026-03-09 | 2026-08-23 | Done | Dependency cleared
ITM-024 | M&A pipeline triage | Issue | High | Hadar Caspit | 2026-02-08 | 2026-09-10 | Done | On track
ITM-025 | Lender refinancing — Tranche A | Issue | Low | Sasha Ouellet | 2026-01-27 | 2026-07-27 | In progress | Pending external review
ITM-026 | Tax compliance — transfer pricing | Action | Low | Daichi Maruyama | 2026-04-19 | 2026-06-04 | In progress | On track
ITM-027 | Sustainability assurance scoping | Action | Medium | Sasha Ouellet | 2026-04-27 | 2026-08-27 | Backlog | Pending external review
ITM-028 | Customer-experience journey map refresh | Action | Low | Hadar Caspit | 2026-01-19 | 2026-09-11 | Done | On track
ITM-029 | Insurance renewal — directors & officers | Action | Low | Hadar Caspit | 2026-05-22 | 2026-11-16 | Done | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Issue | Medium | Daichi Maruyama | 2026-04-16 | 2026-08-07 | Done | Re-baselined this week
ITM-031 | AI use-case prioritisation | Decision | Medium | Mod Admin | 2026-02-23 | 2026-07-16 | Done | Dependency cleared
ITM-032 | Procurement payment-terms harmonisation | Risk | High | Hadar Caspit | 2026-04-27 | 2026-10-21 | Blocked | Dependency cleared