## Register
REG IMD Application Tracker
Source file: REG_IMD_Application_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Hadar Caspit | 2026-01-07 | 2026-07-06 | Blocked | Re-baselined this week
ITM-002 | Capex business case approval pending | Issue | Medium | Hadar Caspit | 2026-03-22 | 2026-11-10 | In progress | Re-baselined this week
ITM-003 | Renewal of MSA — top 5 client | Decision | Low | Daichi Maruyama | 2026-04-25 | 2026-07-26 | In progress | Re-baselined this week
ITM-004 | S/4HANA cut-over readiness gap | Risk | Medium | Daichi Maruyama | 2026-01-02 | 2026-06-12 | In progress | Awaiting input from sponsor
ITM-005 | Talent retention plan — top-200 roles | Issue | Low | Daichi Maruyama | 2026-04-05 | 2026-07-09 | In progress | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Issue | Medium | Mod Admin | 2026-05-03 | 2026-06-25 | Blocked | Pending external review
ITM-007 | Cyber-resilience tabletop exercise | Action | Low | Hadar Caspit | 2026-05-19 | 2026-07-14 | Blocked | Re-baselined this week
ITM-008 | Customer NPS recovery action | Risk | High | Mod Admin | 2026-01-12 | 2026-06-14 | In progress | Pending external review
ITM-009 | Working-capital DSO improvement | Decision | Medium | Sasha Ouellet | 2026-01-08 | 2026-09-11 | Done | Awaiting input from sponsor
ITM-010 | Treasury hedge programme reset | Decision | High | Sasha Ouellet | 2026-01-09 | 2026-10-02 | In progress | On track
ITM-011 | Board-paper template refresh | Issue | Low | Mod Admin | 2026-05-24 | 2026-11-24 | Blocked | Re-baselined this week
ITM-012 | Whistleblowing case — investigation | Risk | Low | Sasha Ouellet | 2026-05-26 | 2026-10-17 | Done | On track
ITM-013 | Inventory ABC re-segmentation | Risk | Low | Hadar Caspit | 2026-04-16 | 2026-09-28 | In progress | On track
ITM-014 | Procurement category sourcing wave | Decision | Medium | Hadar Caspit | 2026-02-27 | 2026-08-11 | Done | Awaiting input from sponsor
ITM-015 | Marketing campaign post-mortem | Issue | Medium | Daichi Maruyama | 2026-02-06 | 2026-11-27 | In progress | Pending external review
ITM-016 | IR investor day — readiness | Decision | Low | Hadar Caspit | 2026-03-07 | 2026-07-28 | In progress | Re-baselined this week
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Daichi Maruyama | 2026-03-10 | 2026-08-09 | Done | Re-baselined this week
ITM-018 | ITGC remediation — access certification | Decision | Medium | Sasha Ouellet | 2026-05-21 | 2026-11-09 | Blocked | Pending external review
ITM-019 | Health & Safety incident review | Action | High | Mod Admin | 2026-03-10 | 2026-06-23 | Done | On track
ITM-020 | Data-quality master-data programme | Issue | Low | Mod Admin | 2026-04-11 | 2026-07-14 | In progress | Dependency cleared
ITM-021 | Operating model — shared services design | Decision | Medium | Hadar Caspit | 2026-05-17 | 2026-10-18 | In progress | On track
ITM-022 | Legal — contract repository migration | Action | Low | Hadar Caspit | 2026-02-26 | 2026-06-01 | In progress | Pending external review
ITM-023 | Group strategy — refresh cadence | Decision | Low | Mod Admin | 2026-04-17 | 2026-08-18 | Blocked | Dependency cleared
ITM-024 | M&A pipeline triage | Decision | Low | Daichi Maruyama | 2026-04-08 | 2026-06-28 | Backlog | Pending external review
ITM-025 | Lender refinancing — Tranche A | Risk | Medium | Daichi Maruyama | 2026-05-13 | 2026-11-02 | In progress | Pending external review
ITM-026 | Tax compliance — transfer pricing | Issue | Medium | Sasha Ouellet | 2026-04-07 | 2026-07-21 | Backlog | Awaiting input from sponsor
ITM-027 | Sustainability assurance scoping | Issue | Medium | Mod Admin | 2026-04-09 | 2026-06-18 | Done | Pending external review
ITM-028 | Customer-experience journey map refresh | Decision | Low | Sasha Ouellet | 2026-03-27 | 2026-09-12 | In progress | Dependency cleared
ITM-029 | Insurance renewal — directors & officers | Issue | High | Daichi Maruyama | 2026-02-02 | 2026-08-20 | Backlog | Pending external review
ITM-030 | Risk appetite statement — refresh | Risk | High | Sasha Ouellet | 2026-02-03 | 2026-06-06 | Backlog | Dependency cleared
ITM-031 | AI use-case prioritisation | Action | Medium | Daichi Maruyama | 2026-05-27 | 2026-09-05 | Blocked | Pending external review
ITM-032 | Procurement payment-terms harmonisation | Risk | Low | Daichi Maruyama | 2026-05-01 | 2026-06-15 | Blocked | Re-baselined this week