## Findings Register
RSK 04 Audit Findings Tracker
Source file: RSK_04_Audit_Findings_Tracker.xlsx
Ref | Title | Severity | Domain | Owner | Raised | Target Close | Status | % Complete
F-2026-001 | Segregation of duties — vendor master maintenance | High | Procurement | Hadar Caspit | 2026-04-23 | 2026-07-01 | Closed | 100%
F-2026-002 | Privileged access review lapsed at SHM division | High | IT | Mod Admin | 2026-02-06 | 2026-07-05 | Closed | 100%
F-2026-003 | Three-way-match override — single remote site | Medium | Finance | Sasha Ouellet | 2026-04-21 | 2026-09-07 | Open | 0%
F-2026-004 | Quarterly counter-cash count inconsistency | Medium | Treasury | Hadar Caspit | 2026-03-18 | 2026-10-03 | Open | 0%
F-2026-005 | KYC refresh overdue on 17 vendor accounts | Medium | Procurement | Sasha Ouellet | 2026-02-16 | 2026-07-02 | Closed | 100%
F-2026-006 | HSE training records incomplete at 2 sites | Medium | HSE | Mod Admin | 2026-04-06 | 2026-09-06 | In progress | 80%
F-2026-007 | Stock count variance >3% at central warehouse | Medium | Operations | Sasha Ouellet | 2026-04-02 | 2026-07-03 | In progress | 65%
F-2026-008 | Capex approval workflow bypass — 1 instance | Low | Finance | Hadar Caspit | 2026-03-15 | 2026-09-18 | Open | 0%
F-2026-009 | Email retention policy not enforced — 2 mailboxes | Low | IT | Mod Admin | 2026-04-10 | 2026-05-13 | In progress | 50%
F-2026-010 | Travel-and-expense receipts missing — 3 staff | Low | Finance | Sasha Ouellet | 2026-01-05 | 2026-10-23 | In progress | 65%
F-2026-011 | Software licence count below installed | Low | IT | Mod Admin | 2026-04-27 | 2026-06-10 | In progress | 65%
F-2026-012 | Insurance certificate expired — 1 vendor | Low | Procurement | Sasha Ouellet | 2026-03-14 | 2026-08-17 | In progress | 80%