## Findings Register
RT 06 Shrinkage Audit
Source file: RT_06_Shrinkage_Audit.xlsx
Ref | Title | Severity | Domain | Owner | Raised | Target Close | Status | % Complete
F-2026-001 | Segregation of duties — vendor master maintenance | High | Procurement | Hadar Caspit | 2026-01-13 | 2026-06-24 | In progress | 80%
F-2026-002 | Privileged access review lapsed at SHM division | High | IT | Mod Admin | 2026-01-08 | 2026-08-07 | Open | 0%
F-2026-003 | Three-way-match override — single remote site | Medium | Finance | Sasha Ouellet | 2026-01-27 | 2026-08-11 | In progress | 50%
F-2026-004 | Quarterly counter-cash count inconsistency | Medium | Treasury | Hadar Caspit | 2026-03-11 | 2026-05-17 | In progress | 50%
F-2026-005 | KYC refresh overdue on 17 vendor accounts | Medium | Procurement | Sasha Ouellet | 2026-01-23 | 2026-06-27 | Open | 0%
F-2026-006 | HSE training records incomplete at 2 sites | Medium | HSE | Mod Admin | 2026-02-17 | 2026-06-06 | In progress | 50%
F-2026-007 | Stock count variance >3% at central warehouse | Medium | Operations | Sasha Ouellet | 2026-02-19 | 2026-08-17 | In progress | 65%
F-2026-008 | Capex approval workflow bypass — 1 instance | Low | Finance | Hadar Caspit | 2026-03-28 | 2026-08-05 | In progress | 35%
F-2026-009 | Email retention policy not enforced — 2 mailboxes | Low | IT | Mod Admin | 2026-03-10 | 2026-05-06 | In progress | 80%
F-2026-010 | Travel-and-expense receipts missing — 3 staff | Low | Finance | Sasha Ouellet | 2026-02-25 | 2026-06-27 | Closed | 100%
F-2026-011 | Software licence count below installed | Low | IT | Mod Admin | 2026-04-09 | 2026-06-14 | In progress | 35%
F-2026-012 | Insurance certificate expired — 1 vendor | Low | Procurement | Sasha Ouellet | 2026-02-23 | 2026-10-18 | Open | 0%