## Register
STR 01 Strategy Tracker
Source file: STR_01_Strategy_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Hadar Caspit | 2026-05-12 | 2026-06-26 | Backlog | Dependency cleared
ITM-002 | Capex business case approval pending | Issue | High | Mod Admin | 2026-05-02 | 2026-11-05 | In progress | On track
ITM-003 | Renewal of MSA — top 5 client | Risk | Low | Sasha Ouellet | 2026-02-16 | 2026-11-24 | Blocked | Dependency cleared
ITM-004 | S/4HANA cut-over readiness gap | Decision | High | Mod Admin | 2026-05-18 | 2026-11-26 | Backlog | Re-baselined this week
ITM-005 | Talent retention plan — top-200 roles | Issue | Low | Mod Admin | 2026-04-01 | 2026-07-08 | Done | On track
ITM-006 | ESG disclosure — Scope 3 data quality | Risk | Medium | Mod Admin | 2026-01-28 | 2026-06-19 | In progress | Re-baselined this week
ITM-007 | Cyber-resilience tabletop exercise | Decision | Medium | Mod Admin | 2026-01-27 | 2026-10-07 | Blocked | Awaiting input from sponsor
ITM-008 | Customer NPS recovery action | Risk | Medium | Hadar Caspit | 2026-05-13 | 2026-06-15 | Blocked | On track
ITM-009 | Working-capital DSO improvement | Action | Low | Sasha Ouellet | 2026-04-26 | 2026-10-27 | In progress | Re-baselined this week
ITM-010 | Treasury hedge programme reset | Decision | Medium | Hadar Caspit | 2026-05-16 | 2026-11-07 | In progress | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Action | Medium | Daichi Maruyama | 2026-03-28 | 2026-06-27 | In progress | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Issue | Medium | Mod Admin | 2026-03-14 | 2026-06-08 | In progress | Awaiting input from sponsor
ITM-013 | Inventory ABC re-segmentation | Issue | Medium | Mod Admin | 2026-03-27 | 2026-06-04 | Blocked | Pending external review
ITM-014 | Procurement category sourcing wave | Decision | Low | Mod Admin | 2026-04-23 | 2026-06-22 | In progress | On track
ITM-015 | Marketing campaign post-mortem | Issue | Low | Sasha Ouellet | 2026-03-18 | 2026-07-20 | In progress | Pending external review
ITM-016 | IR investor day — readiness | Decision | Medium | Daichi Maruyama | 2026-04-03 | 2026-10-14 | In progress | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Decision | Low | Daichi Maruyama | 2026-02-18 | 2026-09-22 | In progress | Awaiting input from sponsor
ITM-018 | ITGC remediation — access certification | Risk | Medium | Daichi Maruyama | 2026-03-08 | 2026-08-17 | In progress | Pending external review
ITM-019 | Health & Safety incident review | Issue | High | Sasha Ouellet | 2026-02-04 | 2026-10-10 | Done | Re-baselined this week
ITM-020 | Data-quality master-data programme | Risk | Low | Hadar Caspit | 2026-01-19 | 2026-06-20 | Done | Pending external review
ITM-021 | Operating model — shared services design | Issue | Medium | Daichi Maruyama | 2026-01-28 | 2026-09-04 | Backlog | On track
ITM-022 | Legal — contract repository migration | Decision | High | Daichi Maruyama | 2026-04-05 | 2026-06-20 | In progress | Dependency cleared
ITM-023 | Group strategy — refresh cadence | Risk | High | Sasha Ouellet | 2026-05-10 | 2026-08-26 | Backlog | Awaiting input from sponsor
ITM-024 | M&A pipeline triage | Risk | Low | Mod Admin | 2026-05-17 | 2026-10-16 | Done | On track
ITM-025 | Lender refinancing — Tranche A | Risk | Low | Daichi Maruyama | 2026-02-28 | 2026-11-12 | Backlog | Awaiting input from sponsor
ITM-026 | Tax compliance — transfer pricing | Action | Medium | Daichi Maruyama | 2026-04-15 | 2026-06-28 | Backlog | Awaiting input from sponsor
ITM-027 | Sustainability assurance scoping | Risk | High | Hadar Caspit | 2026-05-16 | 2026-10-17 | Blocked | Awaiting input from sponsor
ITM-028 | Customer-experience journey map refresh | Risk | Low | Mod Admin | 2026-02-16 | 2026-11-01 | Blocked | On track
ITM-029 | Insurance renewal — directors & officers | Risk | High | Hadar Caspit | 2026-05-09 | 2026-11-16 | Backlog | Dependency cleared
ITM-030 | Risk appetite statement — refresh | Issue | Low | Hadar Caspit | 2026-05-28 | 2026-11-22 | Blocked | On track
ITM-031 | AI use-case prioritisation | Risk | High | Daichi Maruyama | 2026-04-22 | 2026-10-26 | In progress | Pending external review
ITM-032 | Procurement payment-terms harmonisation | Decision | Medium | Daichi Maruyama | 2026-02-04 | 2026-11-19 | Done | Pending external review