## Register
Stewardship Engagement Tracker
Source file: Stewardship_Engagement_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Decision | High | Sasha Ouellet | 2026-05-27 | 2026-06-05 | In progress | Pending external review
ITM-002 | Capex business case approval pending | Risk | Medium | Hadar Caspit | 2026-02-26 | 2026-10-25 | In progress | Re-baselined this week
ITM-003 | Renewal of MSA — top 5 client | Issue | Medium | Sasha Ouellet | 2026-01-04 | 2026-06-23 | In progress | Re-baselined this week
ITM-004 | S/4HANA cut-over readiness gap | Action | Medium | Daichi Maruyama | 2026-04-13 | 2026-07-26 | Done | Dependency cleared
ITM-005 | Talent retention plan — top-200 roles | Issue | Medium | Mod Admin | 2026-05-22 | 2026-06-07 | Done | Re-baselined this week
ITM-006 | ESG disclosure — Scope 3 data quality | Issue | Low | Hadar Caspit | 2026-04-21 | 2026-10-17 | Done | Dependency cleared
ITM-007 | Cyber-resilience tabletop exercise | Action | High | Daichi Maruyama | 2026-04-05 | 2026-09-20 | Backlog | Pending external review
ITM-008 | Customer NPS recovery action | Decision | Medium | Daichi Maruyama | 2026-03-15 | 2026-11-23 | Blocked | Dependency cleared
ITM-009 | Working-capital DSO improvement | Issue | Medium | Hadar Caspit | 2026-03-07 | 2026-09-20 | Backlog | Pending external review
ITM-010 | Treasury hedge programme reset | Issue | Medium | Mod Admin | 2026-01-02 | 2026-11-05 | Done | On track
ITM-011 | Board-paper template refresh | Issue | High | Sasha Ouellet | 2026-03-16 | 2026-10-05 | Backlog | Pending external review
ITM-012 | Whistleblowing case — investigation | Issue | Low | Sasha Ouellet | 2026-01-22 | 2026-07-28 | Backlog | Pending external review
ITM-013 | Inventory ABC re-segmentation | Issue | Low | Sasha Ouellet | 2026-02-07 | 2026-07-21 | In progress | Pending external review
ITM-014 | Procurement category sourcing wave | Risk | Low | Sasha Ouellet | 2026-02-05 | 2026-09-19 | In progress | Awaiting input from sponsor
ITM-015 | Marketing campaign post-mortem | Issue | Medium | Sasha Ouellet | 2026-04-04 | 2026-08-26 | Done | Pending external review
ITM-016 | IR investor day — readiness | Issue | High | Sasha Ouellet | 2026-02-16 | 2026-11-27 | Blocked | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Action | Medium | Sasha Ouellet | 2026-02-28 | 2026-06-22 | In progress | On track
ITM-018 | ITGC remediation — access certification | Decision | High | Daichi Maruyama | 2026-05-22 | 2026-10-10 | In progress | Re-baselined this week
ITM-019 | Health & Safety incident review | Risk | High | Mod Admin | 2026-04-15 | 2026-08-13 | In progress | Awaiting input from sponsor
ITM-020 | Data-quality master-data programme | Action | High | Mod Admin | 2026-04-25 | 2026-10-18 | Blocked | On track
ITM-021 | Operating model — shared services design | Decision | Low | Sasha Ouellet | 2026-04-28 | 2026-06-01 | Backlog | Pending external review
ITM-022 | Legal — contract repository migration | Decision | Low | Hadar Caspit | 2026-03-09 | 2026-11-17 | Done | Re-baselined this week
ITM-023 | Group strategy — refresh cadence | Decision | Medium | Daichi Maruyama | 2026-04-11 | 2026-06-28 | Done | Awaiting input from sponsor
ITM-024 | M&A pipeline triage | Decision | High | Daichi Maruyama | 2026-03-10 | 2026-08-28 | In progress | Re-baselined this week
ITM-025 | Lender refinancing — Tranche A | Action | High | Hadar Caspit | 2026-03-08 | 2026-10-10 | Blocked | Pending external review
ITM-026 | Tax compliance — transfer pricing | Action | Low | Sasha Ouellet | 2026-02-03 | 2026-10-16 | Backlog | Re-baselined this week
ITM-027 | Sustainability assurance scoping | Issue | Medium | Daichi Maruyama | 2026-01-18 | 2026-09-11 | Backlog | Re-baselined this week
ITM-028 | Customer-experience journey map refresh | Action | Low | Mod Admin | 2026-04-10 | 2026-09-25 | Backlog | Dependency cleared
ITM-029 | Insurance renewal — directors & officers | Action | High | Hadar Caspit | 2026-05-01 | 2026-06-04 | Blocked | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Issue | High | Hadar Caspit | 2026-03-15 | 2026-07-25 | In progress | Pending external review
ITM-031 | AI use-case prioritisation | Action | Low | Sasha Ouellet | 2026-05-15 | 2026-11-12 | In progress | Awaiting input from sponsor
ITM-032 | Procurement payment-terms harmonisation | Issue | High | Daichi Maruyama | 2026-01-16 | 2026-11-15 | In progress | Re-baselined this week