## Register
Titan Capital Supervisory Tracker
Source file: Titan_Capital_Supervisory_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Low | Daichi Maruyama | 2026-01-06 | 2026-10-10 | Backlog | Dependency cleared
ITM-002 | Capex business case approval pending | Risk | Low | Mod Admin | 2026-02-25 | 2026-08-07 | In progress | Dependency cleared
ITM-003 | Renewal of MSA — top 5 client | Issue | High | Hadar Caspit | 2026-04-21 | 2026-06-19 | Blocked | On track
ITM-004 | S/4HANA cut-over readiness gap | Issue | Low | Hadar Caspit | 2026-01-06 | 2026-09-03 | Backlog | Awaiting input from sponsor
ITM-005 | Talent retention plan — top-200 roles | Action | Medium | Sasha Ouellet | 2026-02-18 | 2026-10-13 | Backlog | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Decision | Low | Sasha Ouellet | 2026-03-03 | 2026-07-17 | In progress | On track
ITM-007 | Cyber-resilience tabletop exercise | Decision | Low | Mod Admin | 2026-05-18 | 2026-07-20 | Done | Dependency cleared
ITM-008 | Customer NPS recovery action | Issue | Medium | Daichi Maruyama | 2026-03-26 | 2026-07-03 | In progress | Re-baselined this week
ITM-009 | Working-capital DSO improvement | Decision | High | Hadar Caspit | 2026-01-17 | 2026-06-08 | In progress | On track
ITM-010 | Treasury hedge programme reset | Risk | Low | Mod Admin | 2026-05-18 | 2026-10-23 | Backlog | On track
ITM-011 | Board-paper template refresh | Action | Medium | Hadar Caspit | 2026-04-16 | 2026-11-17 | Backlog | Awaiting input from sponsor
ITM-012 | Whistleblowing case — investigation | Decision | Medium | Daichi Maruyama | 2026-04-16 | 2026-07-14 | Done | Awaiting input from sponsor
ITM-013 | Inventory ABC re-segmentation | Risk | Low | Mod Admin | 2026-05-07 | 2026-11-25 | In progress | On track
ITM-014 | Procurement category sourcing wave | Risk | Medium | Daichi Maruyama | 2026-01-22 | 2026-09-01 | In progress | Awaiting input from sponsor
ITM-015 | Marketing campaign post-mortem | Action | High | Mod Admin | 2026-02-24 | 2026-06-12 | Backlog | Pending external review
ITM-016 | IR investor day — readiness | Issue | Low | Sasha Ouellet | 2026-04-12 | 2026-07-19 | In progress | Re-baselined this week
ITM-017 | Internal-audit annual plan refresh | Issue | Medium | Sasha Ouellet | 2026-02-22 | 2026-08-22 | Backlog | Re-baselined this week
ITM-018 | ITGC remediation — access certification | Issue | Medium | Sasha Ouellet | 2026-04-21 | 2026-06-06 | Backlog | On track
ITM-019 | Health & Safety incident review | Issue | Low | Daichi Maruyama | 2026-05-14 | 2026-06-20 | Done | Pending external review
ITM-020 | Data-quality master-data programme | Decision | High | Daichi Maruyama | 2026-04-05 | 2026-07-04 | Backlog | Pending external review
ITM-021 | Operating model — shared services design | Decision | Low | Sasha Ouellet | 2026-02-01 | 2026-11-25 | In progress | Awaiting input from sponsor
ITM-022 | Legal — contract repository migration | Issue | Low | Mod Admin | 2026-01-03 | 2026-11-28 | Blocked | Re-baselined this week
ITM-023 | Group strategy — refresh cadence | Action | Low | Daichi Maruyama | 2026-01-14 | 2026-10-16 | In progress | Pending external review
ITM-024 | M&A pipeline triage | Issue | High | Hadar Caspit | 2026-04-21 | 2026-11-10 | In progress | Dependency cleared
ITM-025 | Lender refinancing — Tranche A | Issue | Low | Daichi Maruyama | 2026-02-13 | 2026-07-19 | Done | Pending external review
ITM-026 | Tax compliance — transfer pricing | Action | High | Daichi Maruyama | 2026-05-11 | 2026-06-03 | Done | Pending external review
ITM-027 | Sustainability assurance scoping | Decision | Low | Daichi Maruyama | 2026-03-05 | 2026-09-10 | In progress | Re-baselined this week
ITM-028 | Customer-experience journey map refresh | Decision | Medium | Hadar Caspit | 2026-03-06 | 2026-08-24 | In progress | On track
ITM-029 | Insurance renewal — directors & officers | Action | Medium | Sasha Ouellet | 2026-03-02 | 2026-09-14 | In progress | Re-baselined this week
ITM-030 | Risk appetite statement — refresh | Risk | High | Daichi Maruyama | 2026-03-13 | 2026-06-07 | Done | Awaiting input from sponsor
ITM-031 | AI use-case prioritisation | Decision | Medium | Sasha Ouellet | 2026-04-24 | 2026-08-06 | In progress | On track
ITM-032 | Procurement payment-terms harmonisation | Risk | Low | Mod Admin | 2026-04-06 | 2026-06-11 | Backlog | Pending external review