## Register
Tracker Glove FDA CBP
Source file: Tracker_Glove_FDA_CBP.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Low | Mod Admin | 2026-05-17 | 2026-06-15 | Done | Pending external review
ITM-002 | Capex business case approval pending | Risk | Medium | Daichi Maruyama | 2026-04-14 | 2026-09-10 | Backlog | Dependency cleared
ITM-003 | Renewal of MSA — top 5 client | Action | Medium | Mod Admin | 2026-03-16 | 2026-10-12 | In progress | Re-baselined this week
ITM-004 | S/4HANA cut-over readiness gap | Risk | Low | Hadar Caspit | 2026-04-10 | 2026-08-11 | In progress | Re-baselined this week
ITM-005 | Talent retention plan — top-200 roles | Action | Medium | Sasha Ouellet | 2026-03-05 | 2026-07-23 | In progress | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Risk | Low | Daichi Maruyama | 2026-04-18 | 2026-09-18 | Backlog | Dependency cleared
ITM-007 | Cyber-resilience tabletop exercise | Issue | Low | Sasha Ouellet | 2026-05-05 | 2026-07-19 | In progress | Re-baselined this week
ITM-008 | Customer NPS recovery action | Action | Medium | Hadar Caspit | 2026-04-25 | 2026-06-17 | Blocked | Pending external review
ITM-009 | Working-capital DSO improvement | Decision | High | Sasha Ouellet | 2026-04-21 | 2026-06-08 | Done | Awaiting input from sponsor
ITM-010 | Treasury hedge programme reset | Action | High | Sasha Ouellet | 2026-03-15 | 2026-09-20 | In progress | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Issue | Medium | Sasha Ouellet | 2026-05-07 | 2026-10-08 | In progress | Pending external review
ITM-012 | Whistleblowing case — investigation | Decision | Low | Mod Admin | 2026-03-11 | 2026-10-14 | Done | On track
ITM-013 | Inventory ABC re-segmentation | Issue | Low | Mod Admin | 2026-02-10 | 2026-06-05 | In progress | Pending external review
ITM-014 | Procurement category sourcing wave | Decision | Medium | Sasha Ouellet | 2026-03-22 | 2026-09-10 | Blocked | On track
ITM-015 | Marketing campaign post-mortem | Decision | Low | Sasha Ouellet | 2026-01-17 | 2026-11-02 | Backlog | Pending external review
ITM-016 | IR investor day — readiness | Issue | Low | Daichi Maruyama | 2026-02-22 | 2026-10-20 | Blocked | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Daichi Maruyama | 2026-03-07 | 2026-08-04 | Done | Re-baselined this week
ITM-018 | ITGC remediation — access certification | Decision | High | Mod Admin | 2026-05-14 | 2026-07-28 | In progress | Re-baselined this week
ITM-019 | Health & Safety incident review | Decision | Medium | Daichi Maruyama | 2026-01-10 | 2026-07-19 | Blocked | Pending external review
ITM-020 | Data-quality master-data programme | Issue | Medium | Mod Admin | 2026-05-03 | 2026-09-09 | In progress | Dependency cleared
ITM-021 | Operating model — shared services design | Decision | Medium | Daichi Maruyama | 2026-03-22 | 2026-10-20 | Done | Awaiting input from sponsor
ITM-022 | Legal — contract repository migration | Risk | Medium | Hadar Caspit | 2026-03-04 | 2026-08-09 | Blocked | Awaiting input from sponsor
ITM-023 | Group strategy — refresh cadence | Issue | Low | Hadar Caspit | 2026-01-10 | 2026-08-15 | Blocked | Pending external review
ITM-024 | M&A pipeline triage | Decision | Low | Hadar Caspit | 2026-03-08 | 2026-09-21 | Blocked | Dependency cleared
ITM-025 | Lender refinancing — Tranche A | Action | Low | Daichi Maruyama | 2026-04-15 | 2026-10-26 | Done | On track
ITM-026 | Tax compliance — transfer pricing | Risk | Low | Hadar Caspit | 2026-04-08 | 2026-06-26 | Backlog | Re-baselined this week
ITM-027 | Sustainability assurance scoping | Action | Low | Sasha Ouellet | 2026-03-02 | 2026-06-17 | Blocked | Re-baselined this week
ITM-028 | Customer-experience journey map refresh | Action | Low | Mod Admin | 2026-03-24 | 2026-07-22 | Blocked | Awaiting input from sponsor
ITM-029 | Insurance renewal — directors & officers | Risk | Medium | Hadar Caspit | 2026-01-16 | 2026-11-13 | Blocked | Re-baselined this week
ITM-030 | Risk appetite statement — refresh | Action | Medium | Sasha Ouellet | 2026-04-21 | 2026-06-12 | In progress | Dependency cleared
ITM-031 | AI use-case prioritisation | Action | Medium | Mod Admin | 2026-01-01 | 2026-07-05 | In progress | On track
ITM-032 | Procurement payment-terms harmonisation | Decision | Medium | Mod Admin | 2026-03-20 | 2026-06-24 | In progress | Pending external review