## Register
Tracker Kepatuhan AELB
Source file: Tracker_Kepatuhan_AELB.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Mod Admin | 2026-05-19 | 2026-07-10 | Blocked | Dependency cleared
ITM-002 | Capex business case approval pending | Issue | High | Daichi Maruyama | 2026-03-23 | 2026-11-05 | Backlog | Pending external review
ITM-003 | Renewal of MSA — top 5 client | Decision | Low | Daichi Maruyama | 2026-02-11 | 2026-11-05 | Backlog | Awaiting input from sponsor
ITM-004 | S/4HANA cut-over readiness gap | Decision | Low | Daichi Maruyama | 2026-03-05 | 2026-07-17 | In progress | Pending external review
ITM-005 | Talent retention plan — top-200 roles | Action | Low | Hadar Caspit | 2026-02-22 | 2026-09-27 | In progress | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Decision | Medium | Hadar Caspit | 2026-05-16 | 2026-08-08 | Done | On track
ITM-007 | Cyber-resilience tabletop exercise | Decision | Medium | Hadar Caspit | 2026-05-12 | 2026-07-21 | In progress | On track
ITM-008 | Customer NPS recovery action | Action | Medium | Mod Admin | 2026-01-05 | 2026-09-24 | In progress | Re-baselined this week
ITM-009 | Working-capital DSO improvement | Risk | Low | Daichi Maruyama | 2026-01-03 | 2026-06-03 | Backlog | On track
ITM-010 | Treasury hedge programme reset | Risk | Low | Hadar Caspit | 2026-03-17 | 2026-07-01 | In progress | Awaiting input from sponsor
ITM-011 | Board-paper template refresh | Risk | High | Mod Admin | 2026-02-09 | 2026-08-19 | Done | Pending external review
ITM-012 | Whistleblowing case — investigation | Decision | Medium | Hadar Caspit | 2026-02-01 | 2026-07-10 | Blocked | Pending external review
ITM-013 | Inventory ABC re-segmentation | Decision | Low | Hadar Caspit | 2026-03-19 | 2026-11-21 | Backlog | Re-baselined this week
ITM-014 | Procurement category sourcing wave | Risk | High | Hadar Caspit | 2026-05-17 | 2026-08-11 | In progress | Dependency cleared
ITM-015 | Marketing campaign post-mortem | Decision | Low | Daichi Maruyama | 2026-01-28 | 2026-09-06 | In progress | Awaiting input from sponsor
ITM-016 | IR investor day — readiness | Decision | Medium | Sasha Ouellet | 2026-03-01 | 2026-10-05 | Backlog | Pending external review
ITM-017 | Internal-audit annual plan refresh | Action | Medium | Sasha Ouellet | 2026-02-27 | 2026-06-20 | In progress | Pending external review
ITM-018 | ITGC remediation — access certification | Action | Low | Mod Admin | 2026-01-18 | 2026-07-17 | In progress | Awaiting input from sponsor
ITM-019 | Health & Safety incident review | Risk | Medium | Mod Admin | 2026-04-17 | 2026-06-07 | In progress | On track
ITM-020 | Data-quality master-data programme | Risk | Low | Mod Admin | 2026-02-23 | 2026-10-21 | Blocked | Awaiting input from sponsor
ITM-021 | Operating model — shared services design | Action | Medium | Sasha Ouellet | 2026-02-07 | 2026-11-26 | Done | Pending external review
ITM-022 | Legal — contract repository migration | Decision | Medium | Sasha Ouellet | 2026-04-25 | 2026-11-23 | Blocked | Re-baselined this week
ITM-023 | Group strategy — refresh cadence | Decision | High | Hadar Caspit | 2026-05-08 | 2026-10-16 | Backlog | Dependency cleared
ITM-024 | M&A pipeline triage | Decision | Low | Hadar Caspit | 2026-04-08 | 2026-11-14 | In progress | Awaiting input from sponsor
ITM-025 | Lender refinancing — Tranche A | Action | Medium | Hadar Caspit | 2026-02-22 | 2026-06-17 | In progress | Pending external review
ITM-026 | Tax compliance — transfer pricing | Decision | Medium | Daichi Maruyama | 2026-04-11 | 2026-06-23 | Blocked | On track
ITM-027 | Sustainability assurance scoping | Action | Medium | Daichi Maruyama | 2026-01-20 | 2026-08-08 | In progress | Re-baselined this week
ITM-028 | Customer-experience journey map refresh | Decision | Low | Mod Admin | 2026-04-02 | 2026-06-17 | In progress | Re-baselined this week
ITM-029 | Insurance renewal — directors & officers | Decision | Medium | Daichi Maruyama | 2026-03-12 | 2026-07-19 | Blocked | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Decision | Low | Hadar Caspit | 2026-03-11 | 2026-06-08 | Blocked | Dependency cleared
ITM-031 | AI use-case prioritisation | Action | Medium | Hadar Caspit | 2026-05-28 | 2026-08-01 | In progress | Pending external review
ITM-032 | Procurement payment-terms harmonisation | Action | High | Hadar Caspit | 2026-03-24 | 2026-06-07 | Done | On track