## Register
Tracker Operasi Zava Education
Source file: Tracker_Operasi_Zava_Education.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Low | Sasha Ouellet | 2026-04-06 | 2026-07-19 | Done | Awaiting input from sponsor
ITM-002 | Capex business case approval pending | Issue | Low | Hadar Caspit | 2026-02-26 | 2026-06-25 | In progress | Pending external review
ITM-003 | Renewal of MSA — top 5 client | Decision | Low | Sasha Ouellet | 2026-01-03 | 2026-09-04 | Backlog | Pending external review
ITM-004 | S/4HANA cut-over readiness gap | Decision | Low | Sasha Ouellet | 2026-02-11 | 2026-06-24 | In progress | On track
ITM-005 | Talent retention plan — top-200 roles | Action | Medium | Sasha Ouellet | 2026-04-10 | 2026-08-25 | Blocked | Pending external review
ITM-006 | ESG disclosure — Scope 3 data quality | Issue | Medium | Mod Admin | 2026-03-02 | 2026-06-16 | Blocked | On track
ITM-007 | Cyber-resilience tabletop exercise | Action | Medium | Mod Admin | 2026-04-05 | 2026-07-18 | Blocked | Dependency cleared
ITM-008 | Customer NPS recovery action | Issue | Low | Hadar Caspit | 2026-03-16 | 2026-06-17 | Backlog | Pending external review
ITM-009 | Working-capital DSO improvement | Decision | Low | Daichi Maruyama | 2026-03-15 | 2026-11-17 | Done | Re-baselined this week
ITM-010 | Treasury hedge programme reset | Issue | Low | Sasha Ouellet | 2026-03-16 | 2026-07-16 | Done | On track
ITM-011 | Board-paper template refresh | Action | High | Mod Admin | 2026-05-23 | 2026-06-27 | Blocked | Pending external review
ITM-012 | Whistleblowing case — investigation | Issue | Medium | Sasha Ouellet | 2026-02-14 | 2026-10-09 | In progress | Dependency cleared
ITM-013 | Inventory ABC re-segmentation | Issue | Low | Daichi Maruyama | 2026-04-27 | 2026-10-07 | In progress | Awaiting input from sponsor
ITM-014 | Procurement category sourcing wave | Issue | Low | Hadar Caspit | 2026-03-03 | 2026-08-14 | Blocked | On track
ITM-015 | Marketing campaign post-mortem | Issue | High | Daichi Maruyama | 2026-03-28 | 2026-08-09 | In progress | Pending external review
ITM-016 | IR investor day — readiness | Issue | Low | Sasha Ouellet | 2026-02-24 | 2026-06-25 | Done | Re-baselined this week
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Daichi Maruyama | 2026-02-28 | 2026-09-04 | In progress | Pending external review
ITM-018 | ITGC remediation — access certification | Risk | Low | Daichi Maruyama | 2026-02-20 | 2026-10-04 | In progress | Pending external review
ITM-019 | Health & Safety incident review | Risk | Low | Mod Admin | 2026-01-05 | 2026-07-12 | Done | Dependency cleared
ITM-020 | Data-quality master-data programme | Risk | Low | Hadar Caspit | 2026-01-12 | 2026-06-22 | Blocked | On track
ITM-021 | Operating model — shared services design | Issue | Low | Hadar Caspit | 2026-05-01 | 2026-06-09 | Backlog | Pending external review
ITM-022 | Legal — contract repository migration | Action | Low | Daichi Maruyama | 2026-01-05 | 2026-11-22 | In progress | Awaiting input from sponsor
ITM-023 | Group strategy — refresh cadence | Issue | High | Sasha Ouellet | 2026-05-05 | 2026-06-17 | Blocked | Dependency cleared
ITM-024 | M&A pipeline triage | Decision | Medium | Daichi Maruyama | 2026-03-03 | 2026-07-15 | In progress | Pending external review
ITM-025 | Lender refinancing — Tranche A | Risk | Low | Hadar Caspit | 2026-02-01 | 2026-09-17 | Blocked | Re-baselined this week
ITM-026 | Tax compliance — transfer pricing | Issue | Low | Sasha Ouellet | 2026-05-08 | 2026-06-16 | Backlog | On track
ITM-027 | Sustainability assurance scoping | Risk | Low | Sasha Ouellet | 2026-04-26 | 2026-06-18 | In progress | Awaiting input from sponsor
ITM-028 | Customer-experience journey map refresh | Issue | Medium | Mod Admin | 2026-02-03 | 2026-07-21 | Done | Re-baselined this week
ITM-029 | Insurance renewal — directors & officers | Decision | Low | Mod Admin | 2026-01-14 | 2026-06-06 | Backlog | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Risk | Low | Mod Admin | 2026-02-17 | 2026-06-26 | Blocked | Pending external review
ITM-031 | AI use-case prioritisation | Action | Medium | Mod Admin | 2026-01-22 | 2026-11-02 | In progress | Dependency cleared
ITM-032 | Procurement payment-terms harmonisation | Issue | Medium | Sasha Ouellet | 2026-02-15 | 2026-09-02 | Backlog | On track