## Register
Zava Connect Operations Tracker
Source file: Zava_Connect_Operations_Tracker.xlsx
ID | Title | Type | Priority | Owner | Raised | Due | Status | Notes
ITM-001 | Vendor onboarding delay — Tier 1 supplier | Risk | Medium | Mod Admin | 2026-02-22 | 2026-07-08 | In progress | Awaiting input from sponsor
ITM-002 | Capex business case approval pending | Decision | High | Mod Admin | 2026-01-17 | 2026-08-22 | Done | On track
ITM-003 | Renewal of MSA — top 5 client | Risk | Medium | Sasha Ouellet | 2026-02-07 | 2026-09-04 | In progress | On track
ITM-004 | S/4HANA cut-over readiness gap | Risk | Low | Daichi Maruyama | 2026-05-21 | 2026-06-13 | In progress | Pending external review
ITM-005 | Talent retention plan — top-200 roles | Decision | High | Sasha Ouellet | 2026-05-05 | 2026-06-07 | Backlog | Dependency cleared
ITM-006 | ESG disclosure — Scope 3 data quality | Action | High | Sasha Ouellet | 2026-03-04 | 2026-11-18 | Done | Dependency cleared
ITM-007 | Cyber-resilience tabletop exercise | Issue | Low | Daichi Maruyama | 2026-05-02 | 2026-06-05 | Backlog | On track
ITM-008 | Customer NPS recovery action | Risk | Low | Sasha Ouellet | 2026-04-04 | 2026-08-12 | In progress | Dependency cleared
ITM-009 | Working-capital DSO improvement | Risk | Low | Daichi Maruyama | 2026-02-07 | 2026-08-11 | In progress | On track
ITM-010 | Treasury hedge programme reset | Action | High | Sasha Ouellet | 2026-02-17 | 2026-11-19 | Done | On track
ITM-011 | Board-paper template refresh | Issue | High | Hadar Caspit | 2026-05-03 | 2026-09-25 | Done | Pending external review
ITM-012 | Whistleblowing case — investigation | Risk | Medium | Mod Admin | 2026-03-24 | 2026-10-11 | Blocked | Re-baselined this week
ITM-013 | Inventory ABC re-segmentation | Decision | Medium | Daichi Maruyama | 2026-01-12 | 2026-11-11 | In progress | Dependency cleared
ITM-014 | Procurement category sourcing wave | Risk | Low | Mod Admin | 2026-03-23 | 2026-08-22 | Done | On track
ITM-015 | Marketing campaign post-mortem | Action | High | Daichi Maruyama | 2026-05-16 | 2026-08-08 | Blocked | Pending external review
ITM-016 | IR investor day — readiness | Issue | High | Hadar Caspit | 2026-03-20 | 2026-09-05 | In progress | Awaiting input from sponsor
ITM-017 | Internal-audit annual plan refresh | Risk | Medium | Sasha Ouellet | 2026-01-12 | 2026-11-03 | Blocked | Re-baselined this week
ITM-018 | ITGC remediation — access certification | Risk | High | Hadar Caspit | 2026-02-10 | 2026-06-20 | Done | Pending external review
ITM-019 | Health & Safety incident review | Decision | Low | Mod Admin | 2026-02-04 | 2026-06-06 | Blocked | Dependency cleared
ITM-020 | Data-quality master-data programme | Risk | Low | Daichi Maruyama | 2026-01-01 | 2026-08-24 | Done | Dependency cleared
ITM-021 | Operating model — shared services design | Action | High | Hadar Caspit | 2026-05-07 | 2026-07-26 | Done | On track
ITM-022 | Legal — contract repository migration | Issue | Medium | Sasha Ouellet | 2026-02-22 | 2026-09-18 | In progress | Awaiting input from sponsor
ITM-023 | Group strategy — refresh cadence | Issue | Medium | Daichi Maruyama | 2026-04-22 | 2026-07-01 | In progress | On track
ITM-024 | M&A pipeline triage | Action | High | Mod Admin | 2026-04-22 | 2026-08-01 | In progress | Dependency cleared
ITM-025 | Lender refinancing — Tranche A | Risk | Medium | Hadar Caspit | 2026-01-09 | 2026-09-17 | In progress | On track
ITM-026 | Tax compliance — transfer pricing | Decision | Medium | Sasha Ouellet | 2026-04-09 | 2026-07-11 | Backlog | Re-baselined this week
ITM-027 | Sustainability assurance scoping | Action | Low | Mod Admin | 2026-03-02 | 2026-08-10 | In progress | Awaiting input from sponsor
ITM-028 | Customer-experience journey map refresh | Action | Medium | Sasha Ouellet | 2026-02-27 | 2026-06-07 | Done | Re-baselined this week
ITM-029 | Insurance renewal — directors & officers | Action | Low | Hadar Caspit | 2026-01-11 | 2026-07-09 | Blocked | Awaiting input from sponsor
ITM-030 | Risk appetite statement — refresh | Issue | Medium | Mod Admin | 2026-01-08 | 2026-06-06 | In progress | Re-baselined this week
ITM-031 | AI use-case prioritisation | Decision | Medium | Daichi Maruyama | 2026-02-15 | 2026-08-02 | Blocked | Dependency cleared
ITM-032 | Procurement payment-terms harmonisation | Decision | High | Mod Admin | 2026-01-12 | 2026-10-20 | Backlog | Awaiting input from sponsor