## Cover
Zava Digital General Insurance
Group Technology — FY2026 Budget vs Actuals
Prepared for: Board Technology & Risk Committee (BTRC)
Owner: Office of the Group CTO
Reporting period: H1 FY2026 (1 Jan – 30 Jun 2026). FY2026 full-year budget shown for context.
Sheets in this workbook
1. Monthly_PnL — 12-month tech budget vs actual by cost centre
2. CostCentres — reference list of IT cost centres and owners
3. ProjectStatus — strategic project portfolio status
Notes
• All figures in RM '000 unless stated otherwise.
• Variance is calculated as Actual minus Budget. Positive = over budget (adverse).
• 10% adverse variance triggers a mandatory Tech Steering corrective action plan.

## CostCentres
Cost Centre Code | Cost Centre | Pillar | Owner / Head
CC-101 | Core Insurance Platform | Applications | Head of Core Systems
CC-102 | Claims & Underwriting Tech | Applications | Head of Claims Tech
CC-103 | Digital Distribution & Portals | Applications | Head of Digital
CC-104 | Data & Analytics Platform | Data & AI | Head of Data
CC-105 | Cybersecurity Operations | Cyber & Resilience | Group CISO
CC-106 | Cloud & Infrastructure | Infrastructure | Head of Infrastructure
CC-107 | End User Computing & Service Desk | Workplace IT | Head of Workplace IT
CC-108 | Network & Telephony | Infrastructure | Network Manager
CC-109 | IT Vendor & Contract Management | Tech Governance | Head of Vendor Mgmt
CC-110 | Tech Risk & RMiT Compliance | Tech Governance | Head of Tech Risk
CC-111 | Innovation & AI Lab | Data & AI | Head of Innovation
CC-112 | PMO & Project Delivery | Tech Governance | Head of PMO

## Monthly_PnL
Cost Centre Code | Cost Centre | Pillar | Owner | Annual Budget (RM '000) | Budget Jan | Actual Jan | Budget Feb | Actual Feb | Budget Mar | Actual Mar | Budget Apr | Actual Apr | Budget May | Actual May | Budget Jun | Actual Jun | Budget Jul | Actual Jul | Budget Aug | Actual Aug | Budget Sep | Actual Sep | Budget Oct | Actual Oct | Budget Nov | Actual Nov | Budget Dec | Actual Dec | YTD Budget | YTD Actual | YTD Variance | Variance % | RAG
CC-101 | Core Insurance Platform | Applications | Head of Core Systems | 28800 | 2370.4 | 2417.8 | 2251.9 | 2364.5 | 2488.9 | 2688 | 2370.4 | 2607.4 | 2370.4 | 2702.3 | 2488.9 | 2936.9 | 2370.4 |  | 2370.4 |  | 2488.9 |  | 2370.4 |  | 2370.4 |  | 2488.9 |  | 14340.9 | 15716.9 | 1376 | 9.595% | Amber
CC-102 | Claims & Underwriting Tech | Applications | Head of Claims Tech | 8400 | 691.4 | 677.6 | 656.8 | 656.8 | 725.9 | 740.4 | 691.4 | 719.1 | 691.4 | 726 | 725.9 | 769.5 | 691.4 |  | 691.4 |  | 725.9 |  | 691.4 |  | 691.4 |  | 725.9 |  | 4182.8 | 4289.4 | 106.6 | 2.549% | Green
CC-103 | Digital Distribution & Portals | Applications | Head of Digital | 6600 | 543.2 | 521.5 | 516 | 505.7 | 570.4 | 570.4 | 543.2 | 554.1 | 543.2 | 564.9 | 570.4 | 598.9 | 543.2 |  | 543.2 |  | 570.4 |  | 543.2 |  | 543.2 |  | 570.4 |  | 3286.4 | 3315.5 | 29.1 | 0.8855% | Green
CC-104 | Data & Analytics Platform | Data & AI | Head of Data | 7200 | 592.6 | 622.2 | 563 | 619.3 | 622.2 | 696.9 | 592.6 | 675.6 | 592.6 | 699.3 | 622.2 | 746.6 | 592.6 |  | 592.6 |  | 622.2 |  | 592.6 |  | 592.6 |  | 622.2 |  | 3585.2 | 4059.9 | 474.7 | 13.24% | Red
CC-105 | Cybersecurity Operations | Cyber & Resilience | Group CISO | 9600 | 790.1 | 790.1 | 750.6 | 765.6 | 829.6 | 871.1 | 790.1 | 853.3 | 790.1 | 869.1 | 829.6 | 937.4 | 790.1 |  | 790.1 |  | 829.6 |  | 790.1 |  | 790.1 |  | 829.6 |  | 4780.1 | 5086.6 | 306.5 | 6.412% | Amber
CC-106 | Cloud & Infrastructure | Infrastructure | Head of Infrastructure | 12000 | 987.7 | 1027.2 | 938.3 | 985.2 | 1037 | 1099.2 | 987.7 | 1037.1 | 987.7 | 1047 | 1037 | 1109.6 | 987.7 |  | 987.7 |  | 1037 |  | 987.7 |  | 987.7 |  | 1037 |  | 5975.4 | 6305.3 | 329.9 | 5.521% | Amber
CC-107 | End User Computing & Service Desk | Workplace IT | Head of Workplace IT | 4800 | 395.1 | 375.3 | 375.3 | 360.3 | 414.8 | 402.4 | 395.1 | 379.3 | 395.1 | 383.2 | 414.8 | 398.2 | 395.1 |  | 395.1 |  | 414.8 |  | 395.1 |  | 395.1 |  | 414.8 |  | 2390.2 | 2298.7 | -91.5 | -3.828% | Green
CC-108 | Network & Telephony | Infrastructure | Network Manager | 3600 | 296.3 | 290.4 | 281.5 | 278.7 | 311.1 | 311.1 | 296.3 | 296.3 | 296.3 | 299.3 | 311.1 | 311.1 | 296.3 |  | 296.3 |  | 311.1 |  | 296.3 |  | 296.3 |  | 311.1 |  | 1792.6 | 1786.9 | -5.7 | -0.318% | Green
CC-109 | IT Vendor & Contract Management | Tech Governance | Head of Vendor Mgmt | 1800 | 148.1 | 142.2 | 140.7 | 133.7 | 155.6 | 150.9 | 148.1 | 142.2 | 148.1 | 140.7 | 155.6 | 149.4 | 148.1 |  | 148.1 |  | 155.6 |  | 148.1 |  | 148.1 |  | 155.6 |  | 896.2 | 859.1 | -37.1 | -4.14% | Green
CC-110 | Tech Risk & RMiT Compliance | Tech Governance | Head of Tech Risk | 2400 | 197.5 | 217.3 | 187.7 | 210.2 | 207.4 | 238.5 | 197.5 | 225.1 | 197.5 | 229.1 | 207.4 | 244.7 | 197.5 |  | 197.5 |  | 207.4 |  | 197.5 |  | 197.5 |  | 207.4 |  | 1195 | 1364.9 | 169.9 | 14.22% | Red
CC-111 | Innovation & AI Lab | Data & AI | Head of Innovation | 3000 | 246.9 | 259.2 | 234.6 | 258.1 | 259.3 | 290.4 | 246.9 | 283.9 | 246.9 | 291.3 | 259.3 | 311.2 | 246.9 |  | 246.9 |  | 259.3 |  | 246.9 |  | 246.9 |  | 259.3 |  | 1493.9 | 1694.1 | 200.2 | 13.4% | Red
CC-112 | PMO & Project Delivery | Tech Governance | Head of PMO | 2400 | 197.5 | 193.5 | 187.7 | 185.8 | 207.4 | 207.4 | 197.5 | 197.5 | 197.5 | 197.5 | 207.4 | 209.5 | 197.5 |  | 197.5 |  | 207.4 |  | 197.5 |  | 197.5 |  | 207.4 |  | 1195 | 1191.2 | -3.8 | -0.318% | Green
| GROUP TOTAL |  |  | 90600

## ProjectStatus
Project Code | Project Name | Sponsor | Pillar | Approved Budget (RM '000) | Spent to Date (RM '000) | Forecast at Completion (RM '000) | Schedule Status | Risk Rating | Comment
PRJ-001 | Core Insurance Platform Modernisation | Group CEO | Applications | 18000 | 14200 | 21800 | Behind | HIGH | Vendor scope creep and integration delays. Re-baselined twice. RM 3.8m forecast overrun.
PRJ-002 | Claims Straight-Through Processing | COO | Applications | 5200 | 3100 | 5400 | On Track | MEDIUM | Pilot in motor claims live; expand to property Q4.
PRJ-003 | Customer Portal & Mobile Refresh | Chief Distribution Officer | Applications | 3600 | 2200 | 3700 | On Track | LOW | Phase 1 launched. Phase 2 in UAT.
PRJ-004 | Enterprise Data Platform (Lakehouse) | Group CFO | Data & AI | 6800 | 4900 | 8100 | Behind | HIGH | Cloud egress costs exceeded estimate. Vendor engaged on cost optimisation.
PRJ-005 | Generative AI for Underwriting Triage | Group CUO | Data & AI | 1500 | 1100 | 1700 | On Track | MEDIUM | Live with two underwriting teams. ROI being measured.
PRJ-006 | Cyber Resilience Uplift (RMiT 2024) | Group CISO | Cyber & Resilience | 4400 | 3500 | 5100 | Behind | HIGH | Incident response retainer renewed at higher rate. Two new BNM controls added in scope.
PRJ-007 | Cloud Migration Wave 2 | Head of Infrastructure | Infrastructure | 7200 | 5400 | 7600 | On Track | MEDIUM | Wave 2 70% complete. FX impact on USD-denominated cloud spend.
PRJ-008 | Workplace M365 / Copilot Rollout | COO | Workplace IT | 2200 | 1300 | 2150 | On Track | LOW | E5 + Copilot licences provisioned to Phase 1 cohort of 350.
PRJ-009 | Vendor Risk Management Platform | Head of Vendor Mgmt | Tech Governance | 900 | 450 | 920 | On Track | LOW | Implementation on schedule. Go-live Q1 next year.
PRJ-010 | RMiT Reporting Automation | Head of Tech Risk | Tech Governance | 1100 | 650 | 1180 | On Track | MEDIUM | Automating BNM RMiT periodic submissions. Phase 1 live.